## Sheet2 (2) (hidden)
S.No. | Dist_Name | PIU_Name | Pack_Number | Road_Name | Total_Length
1 | Balaghat | Balaghat 2 | MP01WBN01 | bithali to mohgaon | 1.5 | 128.6992
2 | Bhind | Bhind 1 | MP04WBN01 | Mahua road to barai via devara | 3.15 | 219.8112
3 | Bhind | Bhind 1 | MP04WBN01 | Barthara road to gethari | 2.5 | 160.1264
4 | Bhind | Bhind 1 | MP04WBN01 | Machand itai road to mahaveer gang via rajpura | 3.85 | 201.5888
5 | Bhind | Bhind 1 | MP04WBN01 | Jaitpur Mathi to Tekri bia khurtala chachai Road | 2.78 | 132.384
6 | Bhopal | Bhopal | MP05WBN01 | NH12 to morga tarasevaniya | 2.96 | 223.9216
7 | Chhatarpur | Chhatarpur | MP06WBN01 | Sahasnagar to hatnai vai gaharwar | 4 | 304.9984
8 | Damoh | Damoh 1 | MP08WBN01 | Mohanpur to khiriya chhakka | 1.6 | 123.6816
9 | Damoh | Damoh 2 | MP08WBN02 | Lidhora to imlatiraha | 2.38 | 156.4976
10 | Dhar | Dhar-3 | MP11WBN01 | Multhan to kherwas | 3.65 | 214.0768
11 | Guna | Guna 1 | MP13WBN 01 | Aron radhougarh road to kakrua | 13.4 | 781.3792
12 | Guna | Guna 2 | MP13WBN 02 | Barsat to Ditalwada via doba | 4.35 | 297.36
13 | Indore | Indore | MP 17 WBN 01 | Khati pipliya to vyaskhedi via haran khedi | 7 | 442.2656
14 | Indore | Indore | MP 17 WBN 01 | Kampel mochi mohalla to undhel marg | 0.8 | 66.2704
15 | Indore | Indore | MP 17 WBN 01 | A.B. Road Dakachya to barhmanpipliya | 8.4 | 519.2432
16 | Indore | Indore | MP 17 WBN 02 | Mhow mndleshwar marg to basipipri choral dame | 2.6 | 250.824
17 | Indore | Indore | MP 17 WBN 02 | Dongra Gaon to naya mhow | 2.2 | 181.8096
18 | Indore | Indore | MP 17 WBN 03 | Jasakakaradiya to garipipliya | 2.5 | 181.0256
19 | Katni | Katni | MP 20 WBN 01 | Mahadev to barheta | 4.8 | 279.2496
20 | Mandsaur | Mandsaur | MP 24 WBN 02 | Ananddham to gelana | 4.25 | 306.432
21 | Mandsaur | Mandsaur | MP 24 WBN 01 | Haripura to saba kheda | 1.3 | 104.7088
22 | Mandsaur | Mandsaur | MP 24 WBN 01 | Ladusa to Bagya | 1.4 | 78.4896
23 | Narsinghpur | Narsinghpur 1 | MP 26 WBN 01 | Rewa nagar pouchmarg | 2.15 | 156.0384
24 | Narsinghpur | Narsinghpur 2 | MP 26 WBN 02 | Bilhari to gundhari (Chargawa) | 2.9 | 174.2944
25 | Narsinghpur | Narsinghpur 2 | MP 26 WBN 02 | Dmohiya to Chilka | 1.7 | 104.8768
26 | Narsinghpur | Narsinghpur 2 | MP 26 WBN 02 | Bilthari to gangai road | 5.3 | 314.3392
27 | Narsinghpur | Narsinghpur 2 | MP 26 WBN 03 | Dhana pithera to kothiya | 3.31 | 202.4512
28 | Narsinghpur | Narsinghpur 2 | MP 26 WBN 03 | Bhudwara chirchira road to merka | 1.26 | 79.8224
29 | Panna | Panna-1 | MP 28 WBN 01 | Birwahi to Ranipura | 8.9 | 349.6192
30 | Rajgarh | Rajgarh -1 | MP 30 WBN 01 | Baday to Machalpur | 9.2 | 624.6352
31 | Rajgarh | Rajgarh -1 | MP 30 WBN 02 | Arinya To Mukundpura via Bhadka | 2.7 | 204.4784
32 | Rajgarh | Rajgarh -1 | MP 30 WBN 02 | Pipladi To Bhojpur NH-12 Khichipur Machalpur to khokriya | 5.6 | 384.7424
33 | Rajgarh | Rajgarh -1 | MP 30 WBN 03 | Bakhed To Sonakheda | 2.35 | 132.1376
34 | Rajgarh | Rajgarh -1 | MP 30 WBN 03 | Lalpura - Dhaturi to Lakhya | 11.2 | 742.28
35 | Rajgarh | Rajgarh 2 | MP 30 WBN 04 | Aklehra to bisakhedi | 6.2 | 428.3888
36 | Rajgarh | Rajgarh 2 | MP 30 WBN 05 | Iklehra Kurawar road gram seka to khagaon khurd | 6.5 | 401.0608
37 | Rajgarh | Rajgarh 2 | MP 30 WBN 06 | Kurawar to talen PMGSY road | 20.6 | 1240.3552
38 | Rajgarh | Rajgarh 2 | MP 30 WBN 07 | Magrana to khedawat | 2.83 | 170.632
39 | Rajgarh | Rajgarh 2 | MP 30 WBN 07 | Sadankhedi to piplod | 5.35 | 338.9232
40 | Ratlam | Ratlam | MP 31 WBN 01 | Kelukhedi to Lakhneti | 4.78 | 288.7786
41 | Ratlam | Ratlam | MP 31 WBN 01 | Dabaria to Gram jhotawad | 2.675 | 150.7643
42 | Ratlam | Ratlam | MP 31 WBN 01 | Jamuniya to Ranayara | 2.95 | 190.12
43 | Ratlam | Ratlam | MP 31 WBN 01 | Barsi to Mandawal | 2.05 | 164.0453
44 | Ratlam | Ratlam | MP 31 WBN 01 | Luni to Kammakhedi | 2.8 | 232.7226
45 | Ratlam | Ratlam | MP 31 WBN 02 | Sukheda to Piplauda via Bhimkuon | 7.78 | 490.672
46 | Rewa | Rewa 1 | MP 32 WBN 03 | Nadha pradanmantri Road to Delhi | 1.7 | 99.4672
47 | Rewa | Rewa 1 | MP 32 WBN 03 | Mankiwar ragherajgarh road to ulhi khsls | 2.05 | 118.2272
48 | Rewa | Rewa 1 | MP 32 WBN 04 | Augdhai Amiliya to Jamui Khurd | 2.7 | 158.9168
49 | Rewa | Rewa 1 | MP 32 WBN 05 | NH7 Kosta to Belha | 3.3 | 231.56
50 | Rewa | Rewa 1 | MP 32 WBN 05 | Dadar to Pathargadi Bamhouri | 3.55 | 270.6256
51 | Sagar | Sagar 1 | MP 33 WBN 01 | Pyasi to beri road | 2.4 | 167.7088
52 | Sagar | Sagar 2 | MP 33 WBN 04 | Bersalla to kheruya | 3.2 | 188.5296
53 | Sagar | Sagar 2 | MP 33 WBN 04 | Bichhua bhavtava to manegaov | 4.98 | 261.8112
54 | Sagar | Sagar 2 | MP 33 WBN 05 | Vijaypura to Bansa kalan road | 6.33 | 392.336
55 | Sehore | Sehore | MP 35 WBN 01 | Pagariya hat to neelbad | 1.3 | 80.7968
56 | Sehore | Sehore | MP 35 WBN 01 | Mugli to rasulpura jod | 2.4 | 195.6976
57 | Sehore | Sehore | MP 35 WBN 01 | Karmankhedi to mundlamahoba | 2.828 | 214.2336
58 | Sehore | Sehore | MP 35 WBN 02 | Panvihar to ghatpalasi | 1.32 | 98.56
59 | Sehore | Sehore | MP 35 WBN 02 | Khari to badjhiri | 0.52 | 33.6672
60 | Sehore | Sehore | MP 35 WBN 03 | Baisad to bhadakui tappar | 2.95 | 199.5952
61 | Sheopur | Sheopur | MP 37 WBN 01 | Agra Piparwas Road To Buddhu k apura | 5.15 | 342.0592
62 | shivpuri | shivpuri 1 | MP 40 WBN 01 | Behgavan to indar | 2.8 | 204.5904
63 | shivpuri | shivpuri 1 | MP 40 WBN 01 | Lalpur to Mubarakpur | 4.05 | 260.5232
64 | shivpuri | shivpuri 1 | MP 40 WBN 02 | Amuhay to Patichak Road | 5.25 | 355.5328
65 | shivpuri | shivpuri 1 | MP 40 WBN 03 | Chakra to sakhnour via kheria | 4.6 | 254.3184
66 | shivpuri | shivpuri 1 | MP 40 WBN 05 | Gram mayapur to ram khadoy pipro | 1.255 | 79.9232
67 | shivpuri | shivpuri 2 | MP 40 WBN 04 | simariya to kudpar | 3.29 | 195.7424
68 | Tikamgarh | Tikamgarh | MP 42 WBN 01 | Birwar to Rest House Jatara | 2.35 | 151.0432
69 | Tikamgarh | Tikamgarh | MP 42 WBN 01 | Toriyo to Amyo Para | 3.21 | 192.4384
70 | Tikamgarh | Tikamgarh | MP 42 WBN 01 | Jawaherpura to UP Border | 2.55 | 160.4736
71 |  | Tikamgarh | MP 42 WBN 01 | Bar to puraniya hirapur | 2.4 | 161.9632
72 | Tikamgarh | Tikamgarh | MP 42 WBN 02 | Dhamna to Patharam Rode | 6.4 | 393.8144
73 | Tikamgarh | Tikamgarh | MP 42 WBN 02 | Gram poha to Ramnagar | 3.96 | 254.2288
74 | Tikamgarh | Tikamgarh | MP 42 WBN 03 | Laxmanpur to Narguda | 5.85 | 364.6384
75 | Tikamgarh | Tikamgarh | MP 42 WBN 03 | Raipur to souni Road | 1.44 | 96.4992
76 | Tikamgarh | Tikamgarh | MP 42 WBN 04 | Majhna palera to kishanpura | 3 | 188.776
77 | Tikamgarh | Tikamgarh | MP 42 WBN 04 | Khargapura to prempura | 2.55 | 165.5808
78 | Tikamgarh | Tikamgarh | MP 42 WBN 04 | Palera Khargapur Road to Lidhora | 2.6 | 167.2384
79 |  | Tikamgarh | MP 42 WBN 04 | Jaitkora to Pahadia Buzurg | 3.2 | 194.7904
80 | Ujjain | Ujjain 1 | MP 43 WBN 04 | Bedavan To Dallaheda | 2.48 | 194.6224
81 | Ujjain | Ujjain 1 | MP 43 WBN 04 | Rohalkhurd to Rohalkala | 2.26 | 164.0576
82 | Ujjain | Ujjain 1 | MP 43 WBN 04 | Borkheda Pitramal To Akyakoli | 4.05 | 286.3728
83 | Ujjain | Ujjain 1 | MP 43 WBN 05 | Bhidavasd Pahuch Marg To no 3 | 3 | 186.8608
84 | Ujjain | Ujjain 1 | MP 43 WBN 05 | Dunalja To Malpura Marg | 2.1 | 146.1712
85 | Ujjain | Ujjain 1 | MP 43 WBN 05 | Ajdavda to Bherupachlana Marg | 1.5 | 101.248
86 | Ujjain | Ujjain 2 | MP 43 WBN 01 | Khajuriya sadar to tarana kanipura road | 2.7 | 187.6896
87 | Ujjain | Ujjain 2 | MP 43 WBN 01 | Najarpura bichod road to gadroli | 2.7 | 172.424
88 | Ujjain | Ujjain 2 | MP 43 WBN 02 | Bhadva to ghatia saidas | 2.7 | 158.6816
89 | Ujjain | Ujjain 2 | MP 43 WBN 02 | Kachhakiya sayed to bakhedanau | 2.8 | 194.8464
90 | Ujjain | Ujjain 2 | MP 43 WBN 02 | Gailakhedi to chingari | 3.3 | 226.4976
91 | Ujjain | Ujjain 2 | MP 43 WBN 03 | Badoda to karanj | 2.45 | 199.8976
92 | Vidisha | Vidisha 2 | MP 45 WBN 01 | Sirabda to kulhan via padariya | 4.45 | 345.9344
93 | Vidisha | Vidisha 2 | MP 45 WBN 02 | Serwasa to kakal khedi | 1.8 | 121.5424
94 |  | fNanokMk | MP07WBN03 | eksBkj ls ekusxkao | 1.88 | 89.96
95 |  | fNanokMk | MP07WBN03 | dqaMkyh[kqnZ ls [kalokMk | 1.53 | 73.93
96 |  | fNanokMk | MP07WBN03 | Rkyfiifj;k ls ?kk?kjkrykbZ | 2.82 | 184.18
97 |  | fNanokMk | MP07WBN05 | gjuHkVk ls cha>kokMk | 3.15 | 171.07
98 |  | fNanokMk | MP07WBN05 | [kkikfcgkjh ls crjh | 3 | 200.59
99 |  | fNanokMk | MP07WBN05 | Pkjxkao ¼flyksVkdyka ½ ls eksgxkaodyk eks;k | 2 | 91.93
100 |  | fNanokMk | MP07WBN06 | fNansokuh ls tkeykikuh | 5.1 | 397.32
101 |  | fNanokMk | MP07WBN06 | vackMh ls ijrkiqj | 4.62 | 306.87
102 |  | fNanokMk | MP07WBN01 | jkghokMk ls flaxksMh dksfYg;k | 1 | 48.96
103 |  | fNanokMk | MP07WBN01 | cksjheky jS;rokMh ls nqykjk | 1.32 | 81.08
104 |  | fNanokMk | MP07WBN02 | Mksc ls fgjhZ | 2.15 | 144.67
105 |  | fNanokMk | MP07WBN02 | lgkou ls ekgqyf>j | 3.41 | 274.66
106 |  | fNanokMk | MP07WBN04 | lqjuknsgh ls cksjnsgh | 3 | 215.87
107 |  | jhok &2 | MP32WBN06 | ,u-,p-&135 e<+k ls xksjek jksM | 1.2 | 143.67
108 |  | jhok &1 | MP32WBN07 | Nqvkjh ls ?kkSa?kV | 3 | 141.81
109 |  | lh/kh | MP 41WBN01 | dsseksj esu jksM ls fprax ,çksp jksM | 1.14 | 53.49
110 |  | lh/kh | MP 41WBN01 | cM+xkvksa guqeku eafnj ls fngqyh [kkl ¼esu jksM½ | 4.35 | 297.12
111 |  | lh/kh | MP 41WBN01 | esu jksM ¼igkM½ ls [kksjck ,çksp jksM | 1.7 | 89.67
112 |  | lh/kh | MP 41WBN02 | venhgk ih,eth,lok; jksM ls xksnfg ih,eth,lok; jksM | 1.48 | 92.23
113 |  | lh/kh | MP 41WBN02 | [kqVsyh lss ykSj ok;k xMbZ | 7.48 | 454.6
114 |  | lh/kh | MP 41WBN03 | eq[; ekxZ es/kkSyh ls eqfLye cLrh igqp ekxZ igkM rd | 4.5 | 285.46
115 |  | lh/kh | MP 41WBN03 | eq[; ekxZ ls ltokuh igqp ekxZ | 1.8 | 105.65
116 |  | lh/kh | MP 41WBN04 | lw;Znhu lkdsr xzke rM+dk ls Mksy ok;k lrisgjk | 6.9 | 469.98
117 |  | lh/kh | MP 41WBN04 | lksu unh ls xq/kyh ¼frykbZ½ igqp ekxZ | 4.22 | 347.35
118 |  | xquk | MP 13WBN03 | chjflagiqjk ls ckykHksV ok;k nkoriqjk | 2.05 | 143.55
119 |  | xquk | MP 13WBN03 | HknkSgh ls cjksfn;kdyka | 2.1 | 126.08
120 |  | xquk | MP 13WBN03 | dMSbZ;k ls vpdyiqj | 1.75 | 118.99
121 |  | [kjxksu | MP 22WBN01 | fliVku ls fcy[ksM+ | 3.5 | 207.54
122 |  | [kjxksu | MP 22WBN01 | eNy xkao ls jsgxkao | 4.6 | 357.58
123 |  | fHk.M&1 | MP 04WBN02 | eN.M jksM ls cgksjhiqjk xka/k | 2.6 | 127.2
124 |  | 'kktkiqj | MP39 WBN01 | vkuanh[ksM+h ls [kjgj[ksM+h | 5.5 | 316.38
125 |  | lkxj&2 | MP 33WBN 06 | iVuk cqtqxZ ls lkoy f[kfj;k ekxZ | 5 | 356.92
126 | Satna | Satna - 2 | MP34WBN01 | Sonversa to Silaura via Karigohi | 8.8
127 | Bhind-2 |  |  | Gaheli to Sayna | 6
128 | Bhind-2 |  |  | Amayan to Tulsipura | 5.1
129 | Bhind-1 |  |  | Bhind lahar rohini jagir Road to Chhidi | 3.5
130 | Sagar-2 |  |  | Ghughar to Baroda | 3.6
131 | Guna-1 |  |  | Patna to Dharanwara | 2.5
132 | Guna-1 |  |  | Aklon to Majhola | 1
133 | Guna-1 |  |  | Muradpur to Golakhedi | 4
134 | Guna-1 |  |  | Panethi to Kalora | 4
135 | Guna-1 |  |  | Simrod to Bhurakhedi | 2
136 | Guna-1 |  |  | Nonpura to Khedela | 2.5
137 | Guna-1 |  |  | Ruthiyai-Dharnawada Road to Chakmeena | 1
138 | Guna-1 |  |  | Muradpur road to Chakmeena | 2.5
139 | Guna-1 |  |  | A.B. Road to Laharkota | 1
140 | Guna-1 |  |  | Poonakhedi to Myana Via Jamra | 8
141 | Guna-1 |  |  | Sagoriya Jamra PMGSY Road | 0.6
142 | Guna-1 |  |  | Jamra to Gajipur | 3.5
143 | Guna-1 |  |  | Imjhara to Piproda Keshraj | 3
510.628
74 | Satna | Satna - 2 | MP34WBN01 | Sonorasha to Salora via Karigohi | 8.8

## Master Sheet (hidden)
Madhya Pradesh Rural Road Development Authority Madhya Pradesh Rural Connectivity Project Provision of Alternative Connectivity Details of Road Sanction for Construction
S.No. | Dist_Name | PIU_Name | Pack_Number | Road_Name | Total_Length | Cost | Construction Cost Excluding GST | Construction Cost as per NIT Excluding GST | Cost of work Awarded Including GST | Cost of work Being Awarded Including GST | Name of PIU Representative | PIU Mobile No. | Name of Contractor and firm | Name of SQC Representative | Road to be first visiting by PIC | [6 empty] | Population as per census 2011 |  |  |  | VF Format | Community Consultation Participant Sheet | [12 empty] | Teacher |  |  | Students |  |  |  | HIV/AIDS |  |  | Labour |  |  | Remark
[15 empty] | First Visit Roads | Second Visit Roads | Visit Road Length | Name of PIC Visit Team | PIC Visiting Date | Progress of work | Document received (Yes/No) | SC | ST | GEN+ OBC | Total |  | ST | SC | OBC | GEN. | Total Male | ST | SC | OBC | GEN. | Total Female | Total | Total PWD | Suggestion | Male | Female | Total Teachers | Girls | Boys | Total Students | No. of Girls Going to High School from your village | Male | Female | Total | Male | Female | Total
1 | Balaghat | Balaghat - 2 | MP01WBN01 | bithali to mohgaon | 1.5 | 128.6992 | 111.12 | 106.64 | 103.204
2 | Bhopal | Bhopal | MP05WBN01 | NH12 to morga tarasevaniya | 2.96 | 223.9216 | 190.94 | 183.26 | 173.441
3 | Chhatarpur | Chhatarpur - 1 | MP06WBN01 | Sahasnagar to hatnai vai gaharwar | 4 | 304.9984 | 262.53 | 249.26 | 208.641
4 | Chhindwara | Chhindwara - 1 | MP07WBN05 | Harnbhata to Bichhawada | 3.15 | 171.07 | 145.19 | 386.22 | 366.3621
5 | Chhindwara | Chhindwara - 1 | MP07WBN05 | Khapabihari To Batri | 3 | 200.59 | 171.91
6 | Chhindwara | Chhindwara - 1 | MP07WBN05 | Chargaon (Silotakala) To Mohgaonkala Moya | 2 | 91.93 | 77.28
7 | Chhindwara | Chhindwara - 1 | MP07WBN06 | CHINDEWANI TO JAMLAPANI | 5.1 | 397.32 | 343.22 | 587.64 | 593.026
8 | Chhindwara | Chhindwara - 1 | MP07WBN06 | AMBADI TO PARTAPUR | 4.62 | 306.87 | 263.5
9 | Chhindwara | Chhindwara - 2 | MP07WBN03 | MOTHAR TO MANEGAON | 1.88 | 89.96 | 75.81 | 280.34 | 255.365
10 | Chhindwara | Chhindwara - 2 | MP07WBN03 | KUDALIKHURD TO KHASWADA | 1.53 | 73.93 | 62.34
11 | Chhindwara | Chhindwara - 2 | MP07WBN03 | TALPIPARIYA TO GHAGHAR TALAI | 2.82 | 184.18 | 157.83
12 | Chhindwara | Chhindwara - 2 | MP07WBN01 | Rahiwada to Singodi Kolhiya | 1 | 48.96 | 41.03 | 105.42 | 99.033
13 | Chhindwara | Chhindwara - 2 | MP07WBN01 | Borimal Ryatwari To Dulara | 1.32 | 81.08 | 68.85
14 | Chhindwara | Chhindwara - 2 | MP07WBN02 | Dob To Hirri | 2.15 | 144.67 | 124.37 | 360 | 358.383
15 | Chhindwara | Chhindwara - 2 | MP07WBN02 | Sahwan To Mahuljhir | 3.41 | 274.66 | 237.26
16 | Chhindwara | Chhindwara - 2 | MP07WBN04 | Malini Surnadehi (Seltiya) To Bordehi Road | 3 | 215.87 | 186.07 | 185.31 | 179.556
17 | Guna | Guna - 1 | MP13WBN01 | Aron radhougarh road to kakrua | 13.4 | 781.3792 | 658.54 | 630.23 | 562.347
18 | Guna | Guna - 2 | MP13WBN02 | Barsat to Ditalwada via doba | 4.35 | 297.36 | 254.41 | 235.77 | 222.264
19 | Guna | Guna-2 | MP13WBN03 | Brisingpura to balabhaint Via Dawatpura | 2.05 | 143.55 | 123.37 | 308.95 | 299.304
20 | Guna | Guna-2 | MP13WBN03 | Bhadodi to Barodiya Kalan | 2.1 | 126.08 | 107.6
21 | Guna | Guna-2 | MP13WBN03 | Kadaiya To Achkalpur | 1.75 | 118.99 | 103.3
22 | Indore | Indore | MP17WBN01 | Khati pipliya to vyaskhedi via haran khedi | 7 | 442.2656 | 377 | 821.56 | 871.809
23 | Indore | Indore | MP17WBN01 | Kampel mochi mohalla to undhel marg | 0.8 | 66.2704 | 57.17
24 | Indore | Indore | MP17WBN01 | A.B. Road Dakachya to barhmanpipliya | 8.4 | 519.2432 | 422.38
25 | Indore | Indore | MP17WBN02 | Mhow mndleshwar marg to basipipri choral dame | 2.6 | 250.824 | 218.43 | 353.72 | 336.011
26 | Indore | Indore | MP17WBN02 | Dongra Gaon to naya mhow | 2.2 | 181.8096 | 156.43
27 | Indore | Indore | MP17WBN03 | Jasakakaradiya to garipipliya | 2.5 | 181.0256 | 155.21 | 145.43 | 151.844
28 | Katni | Katni | MP20WBN01 | Mahadev to barheta | 4.8 | 279.2496 | 236.59 | 226.96 | 227.798
29 | Khargone | Khargone-1 | MP22WBN01 | Machhalgaon to Rehgaon | 4.6 | 357.58 | 309 | 291.66 | 284.132
30 | Mandsaur | Mandsaur | MP24WBN02 | Ananddham to gelana | 4.25 | 306.432 | 262.19 | 245.71 | 231.776
31 | Mandsaur | Mandsaur | MP24WBN01 | Haripura to saba kheda | 1.3 | 104.7088 | 91.02 | 146.01 | 137.902 |  | Mr. G.P. Nagar, SE | 9424077831 |  |  | 1 |  | 1.3 | Mr. Yogesh Kumar Shrivastawa, Mr. Jahangir Khan | 13/01/2021 | B.T., C.C. work completed, Furniture Remains | N | 487 | 50 | 1970 | 2507 |  |  |  | 9 |  | 9 |  |  | 4 |  | 4 | 13 |  |  |  |  | 0 |  |  | 0 |  | 11 | 9 | 20 | 11 | 9 | 20
32 | Mandsaur | Mandsaur | MP24WBN01 | Ladusa to Bagya | 1.4 | 78.4896 | 66.73 |  |  |  | Mr. G.P. Nagar, SE | 9424077831 |  |  | 1 |  | 1.4 | Mr. Yogesh Kumar Shrivastawa, Mr. Jahangir Khan | 13/01/2021 | B.T., C.C. work completed, Furniture Remains | N | 69 | 70 | 171 | 310 |  |  |  | 9 |  | 9 |  |  | 4 |  | 4 | 13 |  |  |  |  | 0 |  |  | 0 |  | 9 | 7 | 16 | 9 | 7 | 16
33 | Narsinghpur | Narsinghpur - 1 | MP26WBN01 | Rewa nagar pouchmarg | 2.15 | 156.0384 | 134.52 | 128.19 | 125.242
34 | Narsinghpur | Narsinghpur - 2 | MP26WBN03 | Dhana pithera to kothiya | 3.31 | 202.4512 | 171.9 | 230.16 | 241.875
35 | Narsinghpur | Narsinghpur - 2 | MP26WBN03 | Bhudwara chirchira road to merka | 1.26 | 79.8224 | 68.05
36 | Rajgarh | Rajgarh -1 | MP30WBN01 | Baday to Machalpur | 9.2 | 624.6352 | 534.89 | 510.8 | 441.767
37 | Rajgarh | Rajgarh -1 | MP30WBN03 | Bakhed To Sonakheda | 2.35 | 132.1376 | 110.86 | 702.2 | 615.226
38 | Rajgarh | Rajgarh -1 | MP30WBN03 | Lalpura - Dhaturi to Lakhya | 11.2 | 742.28 | 631.39
39 | Rajgarh | Rajgarh -2 | MP30WBN04 | Aklehra to bisakhedi | 6.2 | 428.3888 | 367.67 | 349.05 | 314.656
40 | Rajgarh | Rajgarh -2 | MP30WBN05 | Iklehra Kurawar road gram seka to khagaon khurd | 6.5 | 401.0608 | 338.36 | 324.68 | 315.633
41 | Rajgarh | Rajgarh -2 | MP30WBN06 | Kurawar to talen PMGSY road | 20.6 | 1240.3552 | 1044.92 | 999.26 | 955.216
42 | Rajgarh | Rajgarh -2 | MP30WBN07 | Magrana to khedawat | 2.83 | 170.632 | 143.77 | 412.72 | 413.909
43 | Rajgarh | Rajgarh -2 | MP30WBN07 | Sadankhedi to piplod | 5.35 | 338.9232 | 286.37
44 | Ratlam | Ratlam | MP31WBN01 | Kelukhedi to Lakhneti | 4.78 | 288.7786 | 245.32 | 817.11 | 723.419
45 | Ratlam | Ratlam | MP31WBN01 | Dabaria to Gram jhotawad | 2.675 | 150.7643 | 127.43
46 | Ratlam | Ratlam | MP31WBN01 | Jamuniya to Ranayara | 2.95 | 190.12 | 162.34
47 | Ratlam | Ratlam | MP31WBN01 | Barsi to Mandawal | 2.05 | 164.0453 | 140.97
48 | Ratlam | Ratlam | MP31WBN01 | Luni to Kammakhedi | 2.8 | 232.7226 | 201.09
49 | Ratlam | Ratlam | MP31WBN02 | Sukheda to Piplauda via Bhimkuon | 7.78 | 490.672 | 418.22 | 392.78 | 348.723
50 | Rewa | Rewa - 1 | MP32WBN03 | Nadha pradanmantri Road to Delhi | 1.7 | 99.4672 | 84.51 | 177.63 | 166.93
51 | Rewa | Rewa - 1 | MP32WBN03 | Mankiwar ragherajgarh road to ulhi khsls | 2.05 | 118.2272 | 100.72
52 | Rewa | Rewa - 1 | MP32WBN04 | Augdhai Amiliya to Jamui Khurd | 2.7 | 158.9168 | 135.04 | 129.53 | 137.307
53 | Rewa | Rewa - 1 | MP32WBN05 | NH7 Kosta to Belha | 3.3 | 231.56 | 196.73 | 413.45 | 394.374
54 | Rewa | Rewa - 1 | MP32WBN05 | Dadar to Pathargadi Bamhouri | 3.55 | 270.6256 | 232.1
55 | rewa | Rewa-1 | MP32WBN07 | DUARI TO DHAUCHAT | 3 | 141.81 | 118.86 | 118.8 | 111.066
56 | rewa | Rewa-2 | MP32WBN06 | NH-135 Madha To Gurma | 1.2 | 143.67 | 101.56 | 92.68 | 94.31
57 | Sagar | Sagar - 1 | MP33WBN01 | Pyasi to beri road | 2.4 | 167.7088 | 143.88 | 132.67 | 119.887
58 | Sagar | Sagar - 2 | MP33WBN04 | Bersalla to kheruya | 3.2 | 188.5296 | 158.71 | 356.34 | 310.54
59 | Sagar | Sagar - 2 | MP33WBN04 | Bichhua bhavtava to manegaov | 4.98 | 261.8112 | 218.8
60 | Sagar | Sagar - 2 | MP33WBN05 | Vijaypura to Bansa kalan road | 6.33 | 392.336 | 335.51 | 318.33 | 323.133
61 | Sagar | Sagar-2 | MP33WBN06 | Patna Buzurg to Sawalkhiriya Road | 5 | 356.92 | 305.81 | 305.81 | 290.55
62 | Sehore | Sehore | MP35WBN01 | Mugli to rasulpura jod | 2.4 | 195.6976 | 167.44 | 330.97 | 287.9899
63 | Sehore | Sehore | MP35WBN01 | Karmankhedi to mundlamahoba | 2.828 | 214.2336 | 184.59
64 | Sehore | Sehore | MP35WBN02 | Panvihar to ghatpalasi | 1.32 | 98.56 | 83.99 | 108.78 | 99.4897
65 | Sehore | Sehore | MP35WBN02 | Khari to badjhiri | 0.52 | 33.6672 | 29.42
66 | Shajapur | Shajapur | MP39WBN01 | Anandikhedi To Kharharkhedi Road | 5.5 | 316.38 | 269.29 | 253.83 | 262.166
67 | Sheopur | Sheopur | MP37WBN01 | Agra Piparwas Road To Buddhu k apura | 5.15 | 342.0592 | 169.58 | 280.36 | 286.316 |  | Mr. Sanjay Kushwaha, S/E | 9074237923 |  |  | 1 |  | 5.15 | Mr. Yogesh Kumar Shrivastawa, Mr. Jahangir Khan | 26/11/2020 | Earthwork completed, GSB and CD work ongoing |  | 844 | 1159 | 2263 | 4266 |  |  |  | 5 | 4 | 9 |  |  |  |  | 0 | 9 |  | Approach Required |  |  | 0 |  |  | 0 |  | 8 | 4 | 12 | 8 | 4 | 12
68 | shivpuri | shivpuri - 2 | MP40WBN04 | simariya to kudpar | 3.29 | 195.7424 | 215 | 159.68 | 129.2111
69 | shivpuri | shivpuri - 1 | MP40WBN01 | Behgavan to indar | 2.8 | 204.5904 | 292.1 | 379.94 | 319.009 |  | Mr. V.K. Jain, (AM) |  |  |  | 1 |  | 2.8 | Mr. Parvej Pathan, Mr. Sadhan Singh | 28/11/2020 | B.T. completed | N | 1145 | 448 | 3170 | 4763 |  |  | 3 | 6 | 2 | 11 |  |  |  |  | 0 | 11 |  | Enhancement Required |  |  | 0 |  |  | 0 |  | 9 | 6 | 15 | 9 | 6 | 15
70 | shivpuri | shivpuri - 1 | MP40WBN01 | Lalpur to Mubarakpur | 4.05 | 260.5232 | 175.34 |  |  |  | Mr. V.K. Jain, (AM) |  |  |  | 1 |  | 4.05 | Mr. Parvej Pathan, Mr. Sadhan Singh | 27/11/2020 | Earthwork completed | N | 6 | 386 | 372 | 764 |  |  | 3 | 3 |  | 6 | 1 |  | 1 |  | 2 | 8 |  | Enhancement Required |  |  | 0 |  |  | 0 |  | 8 | 3 | 11 | 8 | 3 | 11
71 | shivpuri | shivpuri - 1 | MP40WBN02 | Amuhay to Patichak Road | 5.25 | 355.5328 | 221.22 | 287.58 | 220.579
72 | shivpuri | shivpuri - 1 | MP40WBN03 | Chakra to sakhnour via kheria | 4.6 | 254.3184 | 301.5 | 206.28 | 160.409 |  | Mr. V.K. Jain, (AM) |  |  |  | 1 |  | 4.6 | Mr. Parvej Pathan, Mr. Sadhan Singh | 29/11/2020 | Earthwork completed | N | 239 | 243 | 839 | 1321 |  | 1 | 1 | 4 |  | 6 |  |  |  |  | 0 | 6 |  | Enhancement Required |  |  | 0 |  |  | 0 |  | 9 | 3 | 12 | 9 | 3 | 12
73 | Sidhi | Sidhi | MP41WBN01 | Kymore Main Road To Chitang Approach Road | 1.14 | 53.49 | 44.34 | 371.01 | 361.408
74 | Sidhi | Sidhi | MP41WBN01 | Badagoan-Hanuman mandir To Dihuli Khas (Main Road) | 4.35 | 297.12 | 257.03
75 | Sidhi | Sidhi | MP41WBN01 | Main Road (Pahad) To Khorba Approach Road | 1.7 | 89.67 | 76.03
76 | Sidhi | Sidhi | MP41WBN02 | Amdiha PMGSY Road To Godahi PMGSY Road | 1.48 | 92.23 | 79.11 | 453.47 | 448.822
77 | Sidhi | Sidhi | MP41WBN02 | Khuteli To Lauar Via Gadai | 7.48 | 454.6 | 385.85
78 | Sidhi | Sidhi | MP41WBN03 | Main Road Medhauli To Muslim Basti Approach Road upto Pahad | 4.5 | 285.46 | 244.48 | 332.25 | 324.235
79 | Sidhi | Sidhi | MP41WBN03 | Main Road To Sajwani Approach Road | 1.8 | 105.65 | 92.75
80 | Sidhi | Sidhi | MP41WBN04 | Suryadeen Saket gram Tarka To Dol Via Satpahara | 6.9 | 469.98 | 407.04 | 697.41 | 680.205
81 | Sidhi | Sidhi | MP41WBN04 | Son River To Gudhuli (Tilai) Approach Road | 4.22 | 347.35 | 297.49
82 | Tikamgarh | Tikamgarh | MP42WBN01 | Birwar to Rest House Jatara | 2.35 | 151.0432 | 166.23 | 535.27 | 442.911 |  | Mr. Juber Khan, S/E | 7723902964 |  |  | 1 |  | 2.35 | Mr. Ravi Parihar, Mr. Sunil Verma | 29/11/2020 | B.T., C.C. work completed furniture and shoulder remaining |  | 1158 | 295 | 3797 | 5250 |  | 1 |  |  | 1 | 2 | 1 | 2 | 2 |  | 5 | 7 |  | Approach Required |  |  | 0 |  |  | 0 |  | 10 | 6 | 16 | 10 | 6 | 16
83 | Tikamgarh | Tikamgarh | MP42WBN01 | Toriyo to Amyo Para | 3.21 | 192.4384 | 127.73
84 | Tikamgarh | Tikamgarh | MP42WBN01 | Jawaherpura to UP Border | 2.55 | 160.4736 | 162.07
85 | Tikamgarh | Tikamgarh | MP42WBN01 | Bar to puraniya hirapur | 2.4 | 161.9632 | 135.54
86 | Tikamgarh | Tikamgarh | MP42WBN02 | Dhamna to Patharam Rode | 6.4 | 393.8144 | 137.32 | 521.37 | 417.78 |  | Mr. M.K. Goyal, A/M |  |  | Mr. Anand Kumar, ARE | 1 |  | 6.4 | Mr. Ravi Parihar, Mr. Sunil Verma | 27/11/2020 | Earthwork ongoing |  |  |  |  | 0 |  |  | 2 | 4 | 5 | 11 |  |  |  |  | 0 | 11 |  | Approach Required |  |  | 0 |  |  | 0 |  | 7 | 5 | 12 | 7 | 5 | 12
87 | Tikamgarh | Tikamgarh | MP42WBN02 | Gram poha to Ramnagar | 3.96 | 254.2288 | 332.19 |  |  |  | Mr. M.K. Goyal, A/M |  | Mr. Sourabh Jain | Mr. Anand Kumar, ARE | 1 |  | 3.96 | Mr. Ravi Parihar, Mr. Sunil Verma | 27/11/2020 | B.T. work completed, C.C. furniture and shoulder work remains |  | 0 | 20 | 829 | 849 |  |  |  | 5 |  | 5 |  |  | 3 |  | 3 | 8 |  | Approach Required |  |  | 0 |  |  | 0 |  | 11 | 9 | 20 | 11 | 9 | 20
88 | Tikamgarh | Tikamgarh | MP42WBN03 | Laxmanpur to Narguda | 5.85 | 364.6384 | 214.97 | 370.98 | 291.026 |  | Mr. Juber Khan, S/E | 7723902964 |  |  | 1 |  | 5.85 | Mr. Ravi Parihar, Mr. Sunil Verma | 28/11/2020 | B.T., C.C. work completed, Furniture and shoulder work remains |  | 590 | 0 | 630 | 1220 |  |  | 4 | 3 |  | 7 |  |  |  |  | 0 | 7 |  | Approach Required |  |  | 0 |  |  | 0 |  | 5 | 5 | 10 | 5 | 5 | 10
89 | Tikamgarh | Tikamgarh | MP42WBN03 | Raipur to souni Road | 1.44 | 96.4992 | 307.81 |  |  |  | Mr. Juber Khan, S/E | 7723902964 |  |  | 1 |  | 1.44 | Mr. Ravi Parihar, Mr. Sunil Verma | 28/11/2020 | Work not started |  | 5 | 843 | 201 | 1049 |  | 1 | 3 | 3 |  | 7 |  |  |  |  | 0 | 7 |  | Approach Required |  |  | 0 |  |  | 0 |  | 5 | 5 | 10 | 5 | 5 | 10
90 | Tikamgarh | Tikamgarh | MP42WBN04 | Majhna palera to kishanpura | 3 | 188.776 | 81.79 | 576.95 | 477.769
91 | Tikamgarh | Tikamgarh | MP42WBN04 | Khargapura to prempura | 2.55 | 165.5808 | 159.44 |  |  |  | Mr. Juber Khan, S/E | 7723902964 |  |  | 1 |  | 2.55 | Mr. Ravi Parihar, Mr. Sunil Verma | 29/11/2020 | GSB work ongoing |  | 362 | 0 | 1007 | 1369 |  | 1 | 2 | 6 | 1 | 10 |  | 1 | 1 |  | 2 | 12 |  | Approach Required |  |  | 0 |  |  | 0 |  | 8 | 3 | 11 | 8 | 3 | 11
92 | Tikamgarh | Tikamgarh | MP42WBN04 | Palera Khargapur Road to Lidhora | 2.6 | 167.2384 | 140.1
93 | Tikamgarh | Tikamgarh | MP42WBN04 | Jaitkora to Pahadia Buzurg | 3.2 | 194.7904 | 141.34 |  |  |  | Mr. Juber Khan, S/E | 7723902964 |  |  | 1 |  | 3.2 | Mr. Ravi Parihar, Mr. Sunil Verma | 29/11/2020 | Earthwork completed |  | 542 | 0 | 2428 | 2970 |  | 3 | 2 |  |  | 5 |  |  |  |  | 0 | 5 |  | Approach Required | [7 empty] | 10 | 8 | 18 | 10 | 8 | 18
94 | Ujjain | Ujjain - 1 | MP43WBN04 | Bedavan To Dallaheda | 2.48 | 194.6224 | 164.2 | 524.73 | 461.326
95 | Ujjain | Ujjain - 1 | MP43WBN04 | Rohalkhurd to Rohalkala | 2.26 | 164.0576 | 167.67
96 | Ujjain | Ujjain - 1 | MP43WBN04 | Borkheda Pitramal To Akyakoli | 4.05 | 286.3728 | 140.56
97 | Ujjain | Ujjain - 1 | MP43WBN05 | Bhidavasd Pahuch Marg To no 3 | 3 | 186.8608 | 246.13 | 355.08 | 336.165
98 | Ujjain | Ujjain - 1 | MP43WBN05 | Dunalja To Malpura Marg | 2.1 | 146.1712 | 160.06
99 | Ujjain | Ujjain - 1 | MP43WBN05 | Ajdavda to Bherupachlana Marg | 1.5 | 101.248 | 125.17
100 | Ujjain | Ujjain - 2 | MP43WBN01 | Khajuriya sadar to tarana kanipura road | 2.7 | 187.6896 | 86.64 | 293.33 | 266.592
101 | Ujjain | Ujjain - 2 | MP43WBN01 | Najarpura bichod road to gadroli | 2.7 | 172.424 | 160.48
102 | Ujjain | Ujjain - 2 | MP43WBN02 | Bhadva to ghatia saidas | 2.7 | 158.6816 | 147.2 | 468.71 | 427.498
103 | Ujjain | Ujjain - 2 | MP43WBN02 | Kachhakiya sayed to bakhedanau | 2.8 | 194.8464 | 134.58
104 | Ujjain | Ujjain - 2 | MP43WBN02 | Gailakhedi to chingari | 3.3 | 226.4976 | 166.45
105 | Ujjain | Ujjain - 2 | MP43WBN03 | Badoda to karanj | 2.45 | 199.8976 | 193.88 | 165.74 | 149.4039
106 | Vidisha | Vidisha - 2 | MP45WBN01 | Sirabda to kulhan via padariya | 4.45 | 345.9344 | 295.54 | 283.7 | 260.047
107 | Vidisha | Vidisha - 2 | MP45WBN02 | Serwasa to kakal khedi | 1.8 | 121.5424 | 103.69 | 99.48 | 95.5211
107 |  |  |  | Sub Total | 389.413 | 25584.5627 | 21771.29 | 20819.18 | 19311.8398 | 0 |  |  |  |  | 13 | 0 | 45.05 | 0 | 0 | 0 | 0 | 5447 | 3514 | 17677 | 26638 | 0 | 7 | 20 | 57 | 13 | 97 | 2 | 3 | 15 | 0 | 20 | 117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 73 | 183 | 110 | 73 | 183 | 0
1 | Bhind | Bhind-1 | MP04WBN02 | Machhand road to Bahori pura (Gandh) | 2.6 | 127.2 | 107.22 | 105.17 |  | 118.92
2 | Damoh | Damoh - 1 | MP08WBN01 | Mohanpur to khiriya chhakka | 1.6 | 123.6816 | 105.78 | 101.5 |  | 111.39
3 | Narsinghpur | Narsinghpur - 2 | MP26WBN02 | Bilhari to gundhari (Chargawa) | 2.9 | 174.2944 | 147.98 | 483.68 |  | 484.814
4 | Narsinghpur | Narsinghpur - 2 | MP26WBN02 | Dmohiya to Chilka | 1.7 | 104.8768 | 89.08
5 | Narsinghpur | Narsinghpur - 2 | MP26WBN02 | Bilthari to gangai road | 5.3 | 314.3392 | 267.16
6 | Rajgarh | Rajgarh -1 | MP30WBN02 | Arinya To Mukundpura via Bhadka | 2.7 | 204.4784 | 175.64 | 479.09 |  | 411.0848 | [42 empty] | @46.78 bellow
7 | Rajgarh | Rajgarh -1 | MP30WBN02 | Pipladi To Bhojpur NH-12 Khichipur Machalpur to khokriya | 5.6 | 384.7424 | 327.19
8 | Satna | Satna - 2 | MP34WBN01 | Sonversa to Silaura via Karigohi | 8.8 | 504.75 | 431.56 | 419.52 |  | 372.4112
8 |  |  |  | Sub Total | 31.2 | 1811.1628 | 1544.39 | 1483.79 | 0 | 1498.62
[5 empty] | 420.613 | 27395.7255 | 23315.68 | 22302.97 | 20810.4598
Tender to be recall
1 | Bhind | Bhind - 1 | MP04WBN01 | Mahua road to barai via devara | 3.15 | 219.8112 | 188.32 | 572.19 | [44 empty] | Re-Tender
2 | Bhind | Bhind - 1 | MP04WBN01 | Barthara road to gethari | 2.5 | 160.1264 | 136.99
3 | Bhind | Bhind - 1 | MP04WBN01 | Machand itai road to mahaveer gang via rajpura | 3.85 | 201.5888 | 170.85
4 | Bhind | Bhind - 1 | MP04WBN01 | Jaitpur Mathi to Tekri bia khurtala chachai Road | 2.78 | 132.384 | 111.97
5 | Damoh | Damoh - 2 | MP08WBN02 | Lidhora to imlatiraha | 2.38 | 156.4976 | 131.34 | 127.95 | [44 empty] | No Bid
5 |  |  |  | Sub Total | 14.66 | 870.408 | 739.47 | 700.14
DPR's Under Finalization
1 | Bhind | Bhind-2 | MP04WBN04 | Gaheli to Sayna | 6 | 319.6 | 269.88 | 548.43 | [44 empty] | Bids yet to be invited
2 | Bhind | Bhind-2 | MP04WBN04 | Amayan to Tulsipura | 5.1 | 358.27 | 306.56
3 | Bhind | Bhind-1 | MP04WBN03 | Bhind lahar rohini jagir Road to Chhidi | 3.5 | 207.74 | 176.45 | 166.21
4 | Guna | Guna-1 | MP13WBN04 | Patna to Dharanwara | 2.5 | 182.94 | 151.09 | 2024.464
5 | Guna | Guna-1 | MP13WBN04 | Aklon to Majhola | 1 | 90.04 | 70.29
6 | Guna | Guna-1 | MP13WBN04 | Muradpur to Golakhedi | 4 | 295.2 | 240
7 | Guna | Guna-1 | MP13WBN04 | Panethi to Kalora | 4 | 295.68 | 243.6
8 | Guna | Guna-1 | MP13WBN04 | Simrod to Bhurakhedi | 2 | 149.86 | 122
9 | Guna | Guna-1 | MP13WBN04 | Nonpura to Khedela | 2.5 | 183.21 | 149.58
10 | Guna | Guna-1 | MP13WBN04 | Ruthiyai-Dharnawada Road to Chakmeena | 1 | 84.45 | 69.6
11 | Guna | Guna-1 | MP13WBN04 | Muradpur road to Chakmeena | 2.5 | 190.68 | 155.75
12 | Guna | Guna-1 | MP13WBN04 | A.B. Road to Laharkota | 1 | 73.64 | 60
13 | Guna | Guna-1 | MP13WBN04 | Poonakhedi to Myana Via Jamra | 8 | 550.68 | 444.8
14 | Guna | Guna-1 | MP13WBN04 | Sagoriya Jamra PMGSY Road | 0.6 | 47.1 | 39
15 | Guna | Guna-1 | MP13WBN04 | Jamra to Gajipur | 3.5 | 264.41 | 215.95
16 | Guna | Guna-1 | MP13WBN04 | Imjhara to Piproda Keshraj | 3 | 229.89 | 187.56
17 | Sagar | Sagar-2 | MP33WBN07 | Ghughar to Baroda | 3.6 | 330.02 | 289.26 | 274.24
17 |  |  |  | Sub Total | 53.8 | 3523.39 | 2902.11 | 3013.344
137 |  |  |  | Grand Total | 489.073 | 31789.5235 | 26957.26 | 26016.454 | 19311.8398 | 1498.62

## Social
Madhya Pradesh Rural Road Development Authority Madhya Pradesh Rural Connectivity Project Provision of Alternative Connectivity Details of Road Sanction for Construction
S.No. | Dist_Name | PIU_Name | Pack_Number | Road_Name | Total_Length | Cost | Is it in a Tribal block (Y/N) | Land Transfer required (Y/N) | Land Area (in m2) and type of land (Farmland/homestead/community/other | Any impact on roadside structures[1] (Y/N) | Type of Structure (Private/ community) | Extent of impact in %[2] & Area in sq.mtr | Mitigation for impacts | Does Habitation’s share of ST population exceed 10% total population (N/N) [4] | If response to 10 is Nes, then indicate if FPIC[3] was conducted and broad communitN consent was obtained for project (N/N) | Remarks, if any
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Balaghat | Balaghat - 2 | MP01WBN01 | Bithali to Mohgaon | 1.5 | 128.6992 | Y | Y | 2600 (Other ) | N | N | N | N | Y | Y | MOU obtained
2 | Bhind | Bhind - 1 | MP04WBN01 | Mahua road to barai via devara | 3.15 | 219.8112 | bar: 7 to 15
3 | Bhind | Bhind - 1 |  | Barthara road to gethari | 2.5 | 160.1264 | bar: 7 to 15
4 | Bhind | Bhind - 1 |  | Machand itai road to mahaveer gang via rajpura | 3.85 | 201.5888 | bar: 7 to 15
5 | Bhind | Bhind - 1 |  | Jaitpur Mathi to Tekri bia khurtala chachai Road | 2.78 | 132.384 | bar: 7 to 15
6 | Bhind | Bhind - 1 | MP04WBN02 | Machhand road to Bahori pura (Gandh) | 2.6 | 127.2 | bar: 7 to 15
7 | Bhind | Bhind - 1 | MP04WBN03 | Bhind lahar rohini jagir Road to Chhidi | 3.5 | 207.74 | bar: 7 to 15
8 | Bhind | Bhind - 2 | MP04WBN04 | Gaheli to Sayna | 6 | 319.6 | bar: 7 to 15
9 | Bhind | Bhind - 2 |  | Amayan to Tulsipura | 5.1 | 358.27 | bar: 7 to 15
10 | Bhopal | Bhopal | MP05WBN01 | NH12 to morga tarasevaniya | 2.96 | 223.9216 | bar: 7 to 15
11 | Chhatarpur | Chhatarpur - 1 | MP06WBN01 | Sahasnagar to hatnai vai gaharwar | 4 | 304.9984 | N | Y | 7000 (Other ) | N | N | N | N | N | N | MOU obtained
12 | Chhindwara | Chhindwara - 1 | MP07WBN05 | Harnbhata to Bichhawada | 3.15 | 171.07 | bar: 7 to 15
13 | Chhindwara | Chhindwara - 1 |  | Khapabihari To Batri | 3 | 200.59 | bar: 7 to 15
14 | Chhindwara | Chhindwara - 1 |  | Chargaon (Silotakala) To Mohgaonkala Moya | 2 | 91.93 | bar: 7 to 15
15 | Chhindwara | Chhindwara - 1 | MP07WBN06 | Chindewani to Jamlapani | 5.1 | 397.32 | bar: 7 to 15
16 | Chhindwara | Chhindwara - 1 |  | Ambadi to Partapur | 4.62 | 306.87 | bar: 7 to 15
17 | Chhindwara | Chhindwara - 2 | MP07WBN01 | Rahiwada to Singodi Kolhiya | 1 | 48.96 | bar: 7 to 15
18 | Chhindwara | Chhindwara - 2 |  | Borimal Ryatwari To Dulara | 1.32 | 81.08 | bar: 7 to 15
19 | Chhindwara | Chhindwara - 2 | MP07WBN02 | Dob To Hirri | 2.15 | 144.67 | bar: 7 to 15
20 | Chhindwara | Chhindwara - 2 |  | Sahwan To Mahuljhir | 3.41 | 274.66 | bar: 7 to 15
21 | Chhindwara | Chhindwara - 2 | MP07WBN03 | Mothar to Manegaon | 1.88 | 89.96 | bar: 7 to 15
22 | Chhindwara | Chhindwara - 2 |  | Kudalikhurd to Khaswada | 1.53 | 73.93 | bar: 7 to 15
23 | Chhindwara | Chhindwara - 2 |  | Talpipariya to Ghaghar Talai | 2.82 | 184.18 | bar: 7 to 15
24 | Chhindwara | Chhindwara - 2 | MP07WBN04 | Malini Surnadehi (Seltiya) To Bordehi Road | 3 | 215.87 | bar: 7 to 15
25 | Damoh | Damoh - 1 | MP08WBN01 | Mohanpur to khiriya chhakka | 1.6 | 123.6816 | N | Y | 2000 (Other ) | N | N | N | N | N | N | MOU obtained
26 | Damoh | Damoh - 2 | MP08WBN02 | Lidhora to imlatiraha | 2.38 | 156.4976 | N | Y | 5140 (Other ) | N | N | N | N | N | N | MOU obtained
27 | Guna | Guna - 1 | MP13WBN01 | Aron radhougarh road to kakrua | 13.4 | 781.3792 | bar: 7 to 15
28 | Guna | Guna - 1 | MP13WBN04 | Patna to Dharanwara | 2.5 | 182.94 | bar: 7 to 15
29 | Guna | Guna - 1 |  | Aklon to Majhola | 1 | 90.04 | bar: 7 to 15
30 | Guna | Guna - 1 |  | Muradpur to Golakhedi | 4 | 295.2 | bar: 7 to 15
31 | Guna | Guna - 1 |  | Panethi to Kalora | 4 | 295.68 | bar: 7 to 15
32 | Guna | Guna - 1 |  | Simrod to Bhurakhedi | 2 | 149.86 | bar: 7 to 15
33 | Guna | Guna - 1 |  | Nonpura to Khedela | 2.5 | 183.21 | bar: 7 to 15
34 | Guna | Guna - 1 |  | Ruthiyai-Dharnawada Road to Chakmeena | 1 | 84.45 | bar: 7 to 15
35 | Guna | Guna - 1 |  | Muradpur road to Chakmeena | 2.5 | 190.68 | bar: 7 to 15
36 | Guna | Guna - 1 |  | A.B. Road to Laharkota | 1 | 73.64 | bar: 7 to 15
37 | Guna | Guna - 1 |  | Poonakhedi to Myana Via Jamra | 8 | 550.68 | bar: 7 to 15
38 | Guna | Guna - 1 |  | Sagoriya Jamra PMGSY Road | 0.6 | 47.1 | bar: 7 to 15
39 | Guna | Guna - 1 |  | Jamra to Gajipur | 3.5 | 264.41 | bar: 7 to 15
40 | Guna | Guna - 1 |  | Imjhara to Piproda Keshraj | 3 | 229.89 | bar: 7 to 15
41 | Guna | Guna - 1 | MP13WBN06 | Golakhedi to Barodiyakala | 3.22 | bar: 7 to 15
42 |  |  |  | Golakhedi to Patna | 1.956 | bar: 7 to 15
43 |  |  |  | Pathariya to Chak Churel Via Bhurakhedi | 2.9 | bar: 7 to 15
44 | Guna | Guna - 1 | MP13WBN07 | By pass to By pass Bajrangarh | 1.56 | bar: 7 to 15
45 | Guna | Guna - 2 | MP13WBN02 | Barsat to Ditalwada via doba | 4.35 | 297.36 | bar: 7 to 15
46 | Guna | Guna - 2 | MP13WBN03 | Brisingpura to balabhaint Via Dawatpura | 2.05 | 143.55 | bar: 7 to 15
47 | Guna | Guna - 2 |  | Bhadodi to Barodiya Kalan | 2.1 | 126.08 | bar: 7 to 15
48 | Guna | Guna - 2 |  | Kadaiya To Achkalpur | 1.75 | 118.99 | bar: 7 to 15
49 | Indore | Indore | MP17WBN01 | Khati pipliya to vyaskhedi via haran khedi | 7 | 442.2656 | bar: 7 to 15
50 | Indore | Indore |  | Kampel mochi mohalla to undhel marg | 0.8 | 66.2704 | bar: 7 to 15
51 | Indore | Indore | MP17WBN02 | Mhow mndleshwar marg to basipipri choral dame | 2.6 | 250.824 | N | Y | 5500 (Other ) | Y | Private - Temporary Fensing | N | N | Y | Y | MOU obtained
52 | Indore | Indore |  | Dongra Gaon to naya mhow | 2.2 | 181.8096 | bar: 7 to 15
53 | Katni | Katni | MP20WBN01 | Mahadev to Barheta | 4.8 | 279.2496 | bar: 7 to 15
54 | Khargone | Khargone - 1 | MP22WBN01 | Machhalgaon to Rehgaon | 4.6 | 357.58 | bar: 7 to 15
55 | Mandsaur | Mandsaur | MP24WBN01 | Haripura to saba kheda | 1.3 | 104.7088 | N | Y | 6400 (Other ) | N | N | N | N | N | N | MOU obtained
56 | Mandsaur | Mandsaur |  | Ladusa to Bagya | 1.4 | 78.4896 | bar: 7 to 15
57 | Mandsaur | Mandsaur | MP24WBN02 | Ananddham to gelana | 4.25 | 306.432 | N | Y | 7200 (Other ) | N | N | N | N | N | N | The PAP agreed to provide the land for road construction but feared to sign MOU, Inspire of convincing and detailing about MOU PAP did not singe MOU, there are only 2 PAP detail is enclosed in SMF Doc.
58 | Narsinghpur | Narsinghpur - 1 | MP26WBN01 | Rewa nagar pouch marg | 2.15 | 156.0384 | N | Y | 9900 (Other ) | N | N | N | N | N | N | MOU obtained
59 | Narsinghpur | Narsinghpur - 2 | MP26WBN02 | Bilhari to gundhari (Chargawa) | 2.9 | 174.2944 | bar: 7 to 15
60 | Narsinghpur | Narsinghpur - 2 |  | Dmohiya to Chilka | 1.7 | 104.8768 | bar: 7 to 15
61 | Narsinghpur | Narsinghpur - 2 |  | Bilthari to gangai road | 5.3 | 314.3392 | bar: 7 to 15
62 | Narsinghpur | Narsinghpur - 2 | MP26WBN03 | Dhana pithera to kothiya | 3.31 | 202.4512 | N | Y | 9600 (Other ) | N | N | N | N | N | N | MOU obtained
63 | Narsinghpur | Narsinghpur - 2 |  | Bhudwara chirchira road to merka | 1.26 | 79.8224 | bar: 7 to 15
64 | Rajgarh | Rajgarh - 1 | MP30WBN01 | Baday to Machalpur | 9.2 | 624.6352 | N | Y | 9000 (Other) | N | N | N | N | N | N | MOU obtained
65 | Rajgarh | Rajgarh - 1 | MP30WBN02 | Arinya To Mukundpura via Bhadka | 2.7 | 204.4784 | N | Y | 5600 (Other) | N | N | N | N | N | N | MOU obtained
66 | Rajgarh | Rajgarh - 1 |  | Pipladi To Bhojpur NH-12 Khichipur Machalpur to khokriya | 5.6 | 384.7424 | N | Y | 4400 (Other) | N | N | N | N | N | N | MOU obtained
67 | Rajgarh | Rajgarh - 1 | MP30WBN03 | Bakhed To Sonakheda | 2.35 | 132.1376 | N | Y | 9300 (Other) | N | N | N | N | N | N | MOU obtained
68 | Rajgarh | Rajgarh - 2 | MP30WBN04 | Aklehra to bisakhedi | 6.2 | 428.3888 | bar: 7 to 15
69 | Rajgarh | Rajgarh - 2 | MP30WBN05 | Iklehra Kurawar road gram seka to khagaon khurd | 6.5 | 401.0608 | bar: 7 to 15
70 | Rajgarh | Rajgarh - 2 | MP30WBN07 | Magrana to khedawat | 2.83 | 170.632 | bar: 7 to 15
71 | Rajgarh | Rajgarh - 2 |  | Sadankhedi to piplod | 5.35 | 338.9232 | bar: 7 to 15
72 | Ratlam | Ratlam | MP31WBN01 | Kelukhedi to Lakhneti | 4.78 | 288.7786 | bar: 7 to 15
73 | Ratlam | Ratlam |  | Dabaria to Gram jhotawad | 2.675 | 150.7643 | bar: 7 to 15
74 | Ratlam | Ratlam |  | Jamuniya to Ranayara | 2.95 | 190.12 | bar: 7 to 15
75 | Ratlam | Ratlam |  | Barsi to Mandawal | 2.05 | 164.0453 | N | Y | 9900 (Other ) | N | N | N | N | N | N | MOU obtained
76 | Ratlam | Ratlam |  | Luni to Kammakhedi | 2.8 | 232.7226 | N | Y | 9800 (Other ) | N | N | N | N | N | N | MOU obtained
77 | Ratlam | Ratlam | MP31WBN02 | Sukheda to Piplauda via Bhimkuon | 7.78 | 490.672 | N | Y | 13900 (Other ) | N | N | N | N | Y | Y | MOU obtained
78 | Rewa | Rewa - 1 | MP32WBN03 | Nadha pradanmantri Road to Delhi | 1.7 | 99.4672 | bar: 7 to 15
79 | Rewa | Rewa - 1 |  | Mankiwar ragherajgarh road to ulhi khsls | 2.05 | 118.2272 | bar: 7 to 15
80 | Rewa | Rewa - 1 | MP32WBN04 | Augdhai Amiliya to Jamui Khurd | 2.7 | 158.9168 | bar: 7 to 15
81 | Rewa | Rewa - 1 | MP32WBN05 | NH7 Kosta to Belha | 3.3 | 231.56 | bar: 7 to 15
82 | Rewa | Rewa - 1 |  | Dadar to Pathargadi Bamhouri | 3.55 | 270.6256 | bar: 7 to 15
83 | rewa | Rewa - 1 | MP32WBN07 | Duari to Dhauchat | 3 | 141.81 | bar: 7 to 15
84 | rewa | Rewa - 2 | MP32WBN06 | NH-135 Madha To Gurma | 1.2 | 143.67 | bar: 7 to 15
85 | Sagar | Sagar - 1 | MP33WBN01 | Pyasi to beri road | 2.4 | 167.7088 | bar: 7 to 15
86 | Sagar | Sagar - 2 | MP33WBN04 | Bersalla to kheruya | 3.2 | 188.5296 | bar: 7 to 15
87 | Sagar | Sagar - 2 |  | Bichhua bhavtava to manegaov | 4.98 | 261.8112 | bar: 7 to 15
88 | Sagar | Sagar - 2 | MP33WBN07 | Ghughar to Baroda | 3.6 | 330.02 | bar: 7 to 15
89 | Sehore | Sehore | MP35WBN01 | Mugli to rasulpura jod | 2.4 | 195.6976 | bar: 7 to 15
90 | Sehore | Sehore |  | Karmankhedi to mundlamahoba | 2.828 | 214.2336 | N | Y | 8100 (Other ) | N | N | N | N | N | N | MOU obtained
91 | Sehore | Sehore | MP35WBN02 | Panvihar to ghatpalasi | 1.32 | 98.56 | bar: 7 to 15
92 | Sehore | Sehore |  | Khari to badjhiri | 0.52 | 33.6672 | bar: 7 to 15
93 | Shajapur | Shajapur | MP39WBN01 | Anandikhedi To Kharharkhedi Road | 5.5 | 316.38 | bar: 7 to 15
94 | Sheopur | Sheopur | MP37WBN01 | Agra Piparwas Road To Buddhu k apura | 5.15 | 342.0592 | bar: 7 to 15
95 | shivpuri | Shivpuri - 1 | MP40WBN01 | Behgavan to indar | 2.8 | 204.5904 | bar: 7 to 15
96 | shivpuri | Shivpuri - 1 |  | Lalpur to Mubarakpur | 4.05 | 260.5232 | bar: 7 to 15
97 | shivpuri | Shivpuri - 1 | MP40WBN02 | Amuhay to Patichak Road | 5.25 | 355.5328 | bar: 7 to 15
98 | shivpuri | Shivpuri - 1 | MP40WBN03 | Chakra to sakhnour via kheria | 4.6 | 254.3184 | bar: 7 to 15
99 | shivpuri | Shivpuri - 2 | MP40WBN04 | simariya to kudpar | 3.29 | 195.7424 | N | Y | 6200 (Other ) | N | N | N | N | N | N | MOU obtained
100 | Sidhi | Sidhi | MP41WBN01 | Kymore Main Road To Chitang Approach Road | 1.14 | 53.49 | bar: 7 to 15
101 | Sidhi | Sidhi |  | Badagoan-Hanuman mandir To Dihuli Khas (Main Road) | 4.35 | 297.12 | bar: 7 to 15
102 | Sidhi | Sidhi |  | Main Road (Pahad) To Khorba Approach Road | 1.7 | 89.67 | bar: 7 to 15
103 | Sidhi | Sidhi | MP41WBN02 | Amdiha PMGSY Road To Godahi PMGSY Road | 1.48 | 92.23 | bar: 7 to 15
104 | Sidhi | Sidhi |  | Khuteli To Lauar Via Gadai | 7.48 | 454.6 | bar: 7 to 15
105 | Sidhi | Sidhi |  | Main Road To Sajwani Approach Road | 1.8 | 105.65 | bar: 7 to 15
106 | Sidhi | Sidhi | MP41WBN04 | Suryadeen Saket gram Tarka To Dol Via Satpahara | 6.9 | 469.98 | bar: 7 to 15
107 | Sidhi | Sidhi |  | Son River To Gudhuli (Tilai) Approach Road | 4.22 | 347.35 | bar: 7 to 15
108 | Tikamgarh | Tikamgarh | MP42WBN01 | Birwar to Rest House Jatara | 2.35 | 151.0432 | N | Y | 5000 (Other ) | Y | Private - Kaccha Platform and Temporary Fensing | N | N | N | N | MOU obtained
109 | Tikamgarh | Tikamgarh |  | Toriyo to Amyo Para | 3.21 | 192.4384 | bar: 7 to 15
110 | Tikamgarh | Tikamgarh |  | Bar to puraniya hirapur | 2.4 | 161.9632 | bar: 7 to 15
111 | Tikamgarh | Tikamgarh | MP42WBN02 | Dhamna to Patharam Rode | 6.4 | 393.8144 | N | N | N | N | N | N | N | N | N | Encrochers
112 | Tikamgarh | Tikamgarh |  | Gram poha to Ramnagar | 3.96 | 254.2288 | bar: 7 to 15
113 | Tikamgarh | Tikamgarh | MP42WBN03 | Laxmanpur to Narguda | 5.85 | 364.6384 | bar: 7 to 15
114 | Tikamgarh | Tikamgarh |  | Raipur to souni Road | 1.44 | 96.4992 | N | Y | 4200 (Other ) | N | N | N | N | Y | Y | MOU obtained
115 | Tikamgarh | Tikamgarh |  | Khargapura to prempura | 2.55 | 165.5808 | bar: 7 to 15
116 | Tikamgarh | Tikamgarh |  | Palera Khargapur Road to Lidhora | 2.6 | 167.2384 | N | Y | 7600 (Other ) | N | N | N | N | N | N | MOU obtained
117 | Tikamgarh | Tikamgarh |  | Jaitkora to Pahadia Buzurg | 3.2 | 194.7904 | bar: 7 to 15
118 | Ujjain | Ujjain - 1 | MP43WBN04 | Bedavan To Dallaheda | 2.48 | 194.6224 | N | Y | 8900 (Other ) | N | N | N | N | N | N | MOU Done
119 | Ujjain | Ujjain - 1 |  | Rohalkhurd to Rohalkala | 2.26 | 164.0576 | N | Y | 4900 (Other) | Y | Private - Kaccha Platform | N | N | N | N | MOU Done
120 | Ujjain | Ujjain - 1 |  | Borkheda Pitramal To Akyakoli | 4.05 | 286.3728 | N | Y | 7600 (Other) | N | N | N | N | N | N | MOU Done
121 | Ujjain | Ujjain - 1 | MP43WBN05 | Bhidavasd Pahuch Marg To no 3 | 3 | 186.8608 | N | Y | 6400 (Other) | N | N | N | N | N | N | MOU Done
122 | Ujjain | Ujjain - 1 |  | Dunalja To Malpura Marg | 2.1 | 146.1712 | bar: 7 to 15
123 | Ujjain | Ujjain - 1 |  | Ajdavda to Bherupachlana Marg | 1.5 | 101.248 | bar: 7 to 15
124 | Ujjain | Ujjain - 2 | MP43WBN01 | Khajuriya sadar to tarana kanipura road | 2.7 | 187.6896 | bar: 7 to 15
125 | Ujjain | Ujjain - 2 |  | Najarpura bichod road to gadroli | 2.7 | 172.424 | N | Y | 4850 (Other ) | N | N | N | N | N | N | MOU Done
126 | Ujjain | Ujjain - 2 | MP43WBN02 | Bhadva to ghatia saidas | 2.7 | 158.6816 | N | Y | 5100 (Other) | N | N | N | N | N | N | MOU Done
127 | Ujjain | Ujjain - 2 |  | Kachhakiya sayed to bakhedanau | 2.8 | 194.8464 | N | Y | 5400 (Other) | N | N | N | N | N | N | MOU Done
128 | Ujjain | Ujjain - 2 |  | Gailakhedi to chingari | 3.3 | 226.4976 | N | Y | 6500 (Other) | N | N | N | N | N | N | MOU Done
129 | Ujjain | Ujjain - 2 | MP43WBN03 | Badoda to karanj | 2.45 | 199.8976 | bar: 7 to 15
130 | Vidisha | Vidisha - 2 | MP45WBN01 | Sirabda to kulhan via padariya | 4.45 | 345.9344 | N | Y | 8000 (Other) | N | N | N | N | N | N | MOU Done
131 | Vidisha | Vidisha - 2 | MP45WBN02 | Serwasa to kakal khedi | 1.8 | 121.5424 | N | Y | 8200 (Other ) | N | N | N | N | N | N | MOU Done

## Sheet1 (hidden)
S.No. | Dist_Name | PIU_Name | Pack_Number | Road_Name | Total_Length | Cost | Construction Cost Excluding GST | Construction Cost as per NIT excluding GST | Cost of work awarded Including GST | Cost of work Being awarded included GST
10 | Dhar | Dhar | MP11WBN01 | Multhan to kherwas | 3.65 | 214.0768 |  |  |  |  | delete
29 | Panna | Panna-1 | MP28WBN01 | Birwahi to Ranipura | 8.9 | 349.6192 |  |  |  |  | delete
55 | Sehore | Sehore | MP35WBN01 | Pagariya hat to neelbad | 1.3 | 80.7968 |  |  |  |  | delete
66 | shivpuri | shivpuri - 1 | MP40WBN05 | Gram mayapur to ram khadoy pipro | 1.255 | 79.9232 |  |  |  |  | delete
121 | Khargone | Khargone-1 | MP22WBN01 | Sipatan to Barkhed | 3.5 | 207.54 |  |  |  |  | delete