## Ag-1a
Agenda-R1(a)
Review of PMGSY-1 ,2 balance work in hand as on 1.4.18 and Plan for works to be completed in year 18-19
CGM | District | PIU | Balance work in hand (PMGSY1+2) as on 1st Apr-18 i/c all works sanctioned by GOI whether tender accepted or not |  | Tender yet to be Accepted as on 31st May'18 |  | Balance length in hand for execution (5-7) | PMGSY target given to PIU In Km | Plan for works to be completed in year 2018-19 |  | Plan for Financial Expenditure to be made in year 2018-19 (Rs in Lacs) | Remarks
|  |  | No. Of Road | Length (In Km) | No. Of Road | Length (In Km) |  |  | No. Of Road | Length (In Km)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Bhopal | Bhopal | Bhopal
Bhopal | Raisen | Raisen-1 |  |  | 4 | 34.53
Bhopal | Raisen | Raisen-2 |  |  | 1 | 7.25
Bhopal | Rajgarh | Rajgarh-1 |  |  | 4 | 4.65
Bhopal | Rajgarh | Rajgarh-2 |  |  | 4 | 7.2
Bhopal | Sehore | Sehore
Bhopal | Vidisha | Vidisha-1 |  |  | 4 | 7.55
N'puram | Betul | Betul-1 |  |  | 3 | 16.325
N'puram | Betul | Betul-2 |  |  | 1 | 1.35
N'puram | Betul | Betul-3 |  |  | 2 | 2.32
N'puram | Harda | Harda |  |  | 3 | 59.86
N'puram | Hoshangabad | Hoshangabad1 |  |  | 3 | 25.95
N'puram | Hoshangabad | Hoshangabad2 |  |  | 6 | 55.68
Bhopal | Vidisha | Vidisha-2 |  |  | 2 | 27.75
Bhopal Total |  |  | 0 | 0 | 37 | 250.415
Gwalior | Ashok Nagar | AshokNagar-1 |  |  | 1 | 1.15
Gwalior | Ashok Nagar | AshokNagar-2 |  |  | 1 | 1.1
Gwalior | Bhind | Bhind-1 |  |  | 2 | 2.34
Gwalior | Bhind | Bhind-2 |  |  | 1 | 10.1
Gwalior | Datia | Datia
Gwalior | Guna | Guna-1
Gwalior | Guna | Guna-2
Gwalior | Gwalior | Gwalior
Gwalior | Morena | Morena |  |  | 6 | 34.18
Gwalior | Seopur | Seopur |  |  | 4 | 14.65
Gwalior | Shivpuri | Shivpuri-1 |  |  | 3 | 10.7
Gwalior | Shivpuri | Shivpuri-2 |  |  | 3 | 9.2
Gwalior Total |  |  | 0 | 0 | 21 | 83.42
Indore | Alirajpur | Alirajpur |  |  | 23 | 59.33
Indore | Barwani | Barwani-1 |  |  | 1 | 2.88
Indore | Burhanpur | Burhanpur |  |  | 3 | 19.15
Indore | Dhar | Dhar-1 |  |  | 3 | 32.8
Indore | Dhar | Dhar-2 |  |  | 7 | 16
Indore | Dhar | Dhar-3 |  |  | 10 | 25.89
Indore | Indore | Indore |  |  | 3 | 67.3
Indore | Jhabua | Jhabua |  |  | 26 | 59.6
Indore | Khandwa | Khandwa |  |  | 2 | 1.72
Indore | Khargone | Khargone-1 |  |  | 4 | 10.73
Indore | Khargone | Khargone-2 |  |  | 1 | 22.78
Indore Total |  |  | 0 | 0 | 83 | 318.18
Jabalpur | Balaghat | Balaghat-1 |  |  | 2 | 7.55
Jabalpur | Balaghat | Balaghat-2 |  |  | 6 | 13.59
Jabalpur | Chhindwara | Chhindwara-1
Jabalpur | Chhindwara | Chhindwara-2
Jabalpur | Dindori | Dindori |  |  | 21 | 51.96
Jabalpur | Jabalpur | Jabalpur-1
Jabalpur | Jabalpur | Jabalpur-2 |  |  | 2 | 18.52
Jabalpur | Katni | Katni |  |  | 6 | 51.96
Jabalpur | Mandla | Mandla |  |  | 31 | 62.17
Jabalpur | Narsighpur | Narsighpur-1 |  |  | 3 | 5.95
Jabalpur | Narsighpur | Narsighpur-2 |  |  | 2 | 13.86
Jabalpur | Seoni | Seoni-1 |  |  | 7 | 9.95
Jabalpur | Seoni | Seoni-2 |  |  | 4 | 3.48
Jabalpur Total |  |  | 0 | 0 | 84 | 238.99
Rewa/Shahdol | Anuppur | Anuppur |  |  | 35 | 57.92
Rewa/Shahdol | Rewa | Rewa-1 |  |  | 8 | 20.03
Rewa/Shahdol | Rewa | Rewa-2 |  |  | 2 | 6.2
Rewa/Shahdol | Satna | Satna-1 |  |  | 1 | 11.625
Rewa/Shahdol | Satna | Satna-2
Rewa/Shahdol | Shahdol | Shahdol |  |  | 12 | 27.85
Rewa/Shahdol | Sidhi | Sidhi |  |  | 26 | 77.45
Rewa/Shahdol | Singrauli | Singrauli-1 |  |  | 18 | 52.25
Rewa/Shahdol | Singrauli | Singrauli-2 |  |  | 17 | 55.65
Rewa/Shahdol | Umaria | Umaria |  |  | 11 | 25.44
Rewa/Shahdol Total |  |  | 0 | 0 | 130 | 334.415
Sagar | Chhatarpur | Chhatarpur-1 |  |  | 5 | 10.99
Sagar | Chhatarpur | Chhatarpur-2
Sagar | Damoh | Damoh-1 |  |  | 2 | 56.4
Sagar | Damoh | Damoh-2
Sagar | Panna | Panna-1 |  |  | 4 | 30.95
Sagar | Panna | Panna-2 |  |  | 1 | 1.6
Sagar | Sagar | Sagar-1 |  |  | 10 | 86.891
Sagar | Sagar | Sagar-2 |  |  | 1 | 23.254
Sagar | Tikamgarh | Tikamgarh |  |  | 16 | 26.2
Sagar Total |  |  | 0 | 0 | 39 | 236.285
Ujjain | Dewas | Dewas-1 |  |  | 1 | 22
Ujjain | Dewas | Dewas-2 |  |  | 2 | 35.49
Ujjain | Mandsour | Mandsour |  |  | 1 | 6.6
Ujjain | Neemuch | Neemuch
Ujjain | Ratlam | Ratlam |  |  | 2 | 16.76
Ujjain | Shajapur | Shajapur-1 |  |  | 2 | 42.5
Ujjain | Agar | Agar |  |  | 2 | 1.8
Ujjain | Ujjain | Ujjain-1 |  |  | 4 | 12.88
Ujjain | Ujjain | Ujjain-2 |  |  | 3 | 7.16
Ujjain Total |  |  | 0 | 0 | 17 | 145.19
Grand Total |  |  | 0 | 0 | 411 | 1606.895

## Ag-1b
Agenda-R1(b)
PMGSY target and completion plan for 2018-19
CGM | District | PIU | Target for the Year (In Km) | April-May 18 |  | Spil over for next month | 2018-06-01 |  | 2018-07-18 |  | 2018-08-18 |  | 2018-09-18 |  | 2018-10-18 |  | 2018-11-18 |  | 2018-12-18 |  | 2019-01-19 |  | 2019-02-19 |  | 2019-03-18
|  |  |  | Target (In Km) | Achievement plan (In Km) |  | Target (In Km) | Achievement plan (In Km) | Target (In Km) | Achievement plan (In Km) | Target (In Km) | Achievement plan (In Km) | Target (In Km) | Achievement plan (In Km) | Target (In Km) | Achievement plan (In Km) | Target (In Km) | Achievement plan (In Km) | Target (In Km) | Achievement plan(In Km) | Target (In Km) | Achievement plan (In Km) | Target (In Km) | Achievement plan (In Km) | Target (In Km) | Achievement plan (In Km)
1 | 2 | 3 |  | 4 |  | 5 | 6 | 7 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Bhopal | Bhopal | Bhopal | 28.476 | 3.1324 |  |  | 0.85428 |  | 0.56952 | 9: 0.56952; 11: 0.56952; 13: 3.4171; 15: 3.4171; 17: 4.2714; 19: 4.2714; 21: 3.7019; 23: 3.7019
Bhopal | Raisen | Raisen-1 | 11.163 | 4 |  |  | 1 |  |  | 13: 3; 15: 3.16
Bhopal | Raisen | Raisen-2 | 12.961 | 4 |  |  | 1 |  |  | 13: 3; 15: 3.7; 17: 1.26
Bhopal | Rajgarh | Rajgarh-1 | 57.024 | 4.5619 |  |  | 3.4214 |  | 1.1405 | 9: 1.1405; 11: 1.1405; 13: 6.8429; 15: 6.8429; 17: 8.5536; 19: 8.5536; 21: 7.4131; 23: 7.4131
Bhopal | Rajgarh | Rajgarh-2 | 63.731 | 5.0985 |  |  | 3.8239 |  | 1.2746 | 9: 1.2746; 11: 1.2746; 13: 7.6477; 15: 7.6477; 17: 9.5596; 19: 9.5596; 21: 8.285; 23: 8.285
Bhopal | Sehore | Sehore | 85.75 | 6.86 |  |  | 5.145 |  | 1.715 | 9: 1.715; 11: 1.715; 13: 10.29; 15: 10.29; 17: 12.8625; 19: 12.8625; 21: 11.1475; 23: 11.1475
Bhopal | Vidisha | Vidisha-1 | 19.092 | 3.35 |  |  | 0.8 |  |  | 13: 2.291; 15: 2.291; 17: 2.8638; 19: 2.8638; 21: 2.6; 23: 2
Bhopal | Vidisha | Vidisha-2 | 41.811 | 3.3449 |  |  | 2.5087 |  | 0.83622 | 9: 0.83622; 11: 0.83622; 13: 5.0173; 15: 5.0173; 17: 6.2717; 19: 6.2717; 21: 5.4354; 23: 5.4354
N'puram | Betul | Betul-1 | 19.04 | 1.5232 |  |  | 1.1424 |  |  | 13: 2.2848; 15: 2.2848; 17: 2.856; 19: 2.856; 21: 2.4752; 23: 2.4752
N'puram | Betul | Betul-2 | 18.195 | 1.4556 |  |  | 1.0917 |  |  | 13: 2.1834; 15: 2.1834; 17: 2.7292; 19: 2.7292; 21: 2.3654; 23: 2.3654
N'puram | Betul | Betul-3 | 3.72 | 2 |  |  | 1.72 |  | 0
N'puram | Harda | Harda | 30.23 | 3.3253 |  |  | 0.9069 |  | 0.6046 | 9: 0.6046; 11: 0.6046; 13: 3.6276; 15: 3.6276; 17: 4.5345; 19: 4.5345; 21: 3.9299; 23: 3.9299
N'puram | Hoshangabad | Hoshangabad-2 | 14.082 | 4 |  |  | 2 |  |  | 13: 4; 15: 3; 17: 1.08
Gwalior | Ashoknagar | Ashoknagar-1 | 29.706 | 3.2677 |  |  | 0.89118 |  | 0.59412 | 9: 0.59412; 11: 0.59412; 13: 3.5647; 15: 3.5647; 17: 4.4559; 19: 4.4559; 21: 3.8618; 23: 3.8618
Gwalior | Ashoknagar | Ashoknagar-2 | 59.345 | 4.7476 |  |  | 3.5607 |  | 1.1869 | 9: 1.1869; 11: 1.1869; 13: 7.1214; 15: 7.1214; 17: 8.9017; 19: 8.9017; 21: 7.7149; 23: 7.7149
Gwalior | Bhind | Bhind-1 | 8.242 | 2 |  |  | 1 |  | 0.16484 | 9: 0.16484; 11: 0.16484; 13: 4; 15: 1
Gwalior | Bhind | Bhind-2 | 6.25 | 2 |  |  | 1 |  | 0 | 9: 0; 11: 0; 13: 1.25; 15: 2
Gwalior | Datia | Datia | 31.142 | 3.4256 |  |  | 0.93426 |  | 0.62284 | 9: 0.62284; 11: 0.62284; 13: 3.737; 15: 3.737; 17: 4.6713; 19: 4.6713; 21: 4.0485; 23: 4.0485
Gwalior | Guna | Guna-1 | 49.26 | 3.9408 |  |  | 2.9556 |  | 0.9852 | 9: 0.9852; 11: 0.9852; 13: 5.9112; 15: 5.9112; 17: 7.389; 19: 7.389; 21: 6.4038; 23: 6.4038
Gwalior | Guna | Guna-2 | 43.48 | 3.4784 |  |  | 2.6088 |  | 0.8696 | 9: 0.8696; 11: 0.8696; 13: 5.2176; 15: 5.2176; 17: 6.522; 19: 6.522; 21: 5.6524; 23: 5.6524
Gwalior | Gwalior | Gwalior | 59.095 | 4.7276 |  |  | 3.5457 |  | 1.1819 | 9: 1.1819; 11: 1.1819; 13: 7.0914; 15: 7.0914; 17: 8.8643; 19: 8.8643; 21: 7.6824; 23: 7.6824
Gwalior | Morena | Morena | 13.529 | 4 |  |  | 1 |  |  | 13: 2; 15: 3; 17: 3.53
Gwalior | Seopur | Seopur | 126.54 | 10.1232 |  |  | 7.5924 |  | 2.5308 | 9: 2.5308; 11: 2.5308; 13: 15.1848; 15: 15.1848; 17: 18.981; 19: 18.981; 21: 16.4502; 23: 16.4502
Gwalior | Shivpuri | Shivpuri-1 | 47.495 | 3.7996 |  |  | 2.8497 |  | 0.9499 | 9: 0.9499; 11: 0.9499; 13: 5.6994; 15: 5.6994; 17: 7.1242; 19: 7.1242; 21: 6.1743; 23: 6.1743
Gwalior | Shivpuri | Shivpuri-2 | 78.265 | 6.2612 |  |  | 4.6959 |  | 1.5653 | 9: 1.5653; 11: 1.5653; 13: 9.3918; 15: 9.3918; 17: 11.7397; 19: 11.7397; 21: 10.1745; 23: 10.1745
Indore | Alirajpur | Alirajpur | 85.18 | 6.8144 |  |  | 5.1108 |  | 1.7036 | 9: 1.7036; 11: 1.7036; 13: 10.2216; 15: 10.2216; 17: 12.777; 19: 12.777; 21: 11.0734; 23: 11.0734
Indore | Barwani | Barwani | 143.894 | 11.5115 |  |  | 8.6336 |  | 2.8779 | 9: 2.8779; 11: 2.8779; 13: 17.2673; 15: 17.2673; 17: 21.5841; 19: 21.5841; 21: 18.7062; 23: 18.7062
Indore | Burhanpur | Burhanpur | 7.156 | 2 |  |  | 1 |  | 0 | 9: 0; 11: 0; 13: 2; 15: 2.16
Indore | Dhar | Dhar-1 | 23.255 | 2.558 |  |  | 0.69765 |  | 0.4651 | 9: 0.4651; 11: 0.4651; 13: 2.7906; 15: 2.7906; 17: 3.4882; 19: 3.4882; 21: 3.0231; 23: 3.0231
Indore | Dhar | Dhar-2 | 40.61 | 3.2488 |  |  | 2.4366 |  | 0.8122 | 9: 0.8122; 11: 0.8122; 13: 4.8732; 15: 4.8732; 17: 6.0915; 19: 6.0915; 21: 5.2793; 23: 5.2793
Indore | Dhar | Dhar-3 | 35.62 | 3.9182 |  |  | 1.0686 |  | 0.7124 | 9: 0.7124; 11: 0.7124; 13: 4.2744; 15: 4.2744; 17: 5.343; 19: 5.343; 21: 4.6306; 23: 4.6306
Indore | Indore | Indore | 39.211 | 4.3132 |  |  | 1.1763 |  | 0.78422 | 9: 0.78422; 11: 0.78422; 13: 4.7053; 15: 4.7053; 17: 5.8816; 19: 5.8816; 21: 5.0974; 23: 5.0974
Indore | Jhabua | Jhabua | 69.05 | 5.524 |  |  | 4.143 |  | 1.381 | 9: 1.381; 11: 1.381; 13: 8.286; 15: 8.286; 17: 10.3575; 19: 10.3575; 21: 8.9765; 23: 8.9765
Indore | Khaggone | Khaggone-1 | 38.575 | 4.2433 |  |  | 1.1573 |  | 0.7715 | 9: 0.7715; 11: 0.7715; 13: 4.629; 15: 4.629; 17: 5.7862; 19: 5.7862; 21: 5.0148; 23: 5.0148
Indore | Khargone | Khargone-2 | 0.379 | 0.38
Indore | Khandwa | Khandwa | 24.732 | 2.7205 |  |  | 0.74196 |  | 0.49464 | 9: 0.49464; 11: 0.49464; 13: 2.9678; 15: 2.9678; 17: 3.7098; 19: 3.7098; 21: 3.2152; 23: 3.2152
Jabalpur | Balaghat | Balaghat-1 | 68.705 | 5.4964 |  |  | 4.1223 |  | 1.3741 | 9: 1.3741; 11: 1.3741; 13: 8.2446; 15: 8.2446; 17: 10.3058; 19: 10.3058; 21: 8.9317; 23: 8.9317
Jabalpur | Balaghat | Balaghat-2 | 17.17 | 2.03 |  |  | 0.5 |  |  | 13: 2.0604; 15: 2.0604; 17: 2.5755; 19: 2.5755; 21: 2.2321; 23: 2.2321
Jabalpur | Chhindwara | Chhindwara-1 | 149.62 | 10.1888 |  |  | 7.6416 |  | 2.5472 | 9: 2.5472; 11: 2.5472; 13: 15.2832; 15: 15.2832; 17: 19.104; 19: 19.104; 21: 16.5568; 23: 16.5568
Jabalpur | Chhindwara | Chhindwara-2 | 147.82 | 7.1336 |  |  | 5.3502 |  | 1.7834 | 9: 1.7834; 11: 1.7834; 13: 10.7004; 15: 10.7004; 17: 13.3755; 19: 13.3755; 21: 11.5921; 23: 11.5921
Jabalpur | Chhindwara | Chhindwara-3 |  | 6.3094 |  |  | 4.7321 |  | 1.5774 | 9: 1.5774; 11: 1.5774; 13: 9.4642; 15: 9.4642; 17: 11.8302; 19: 11.8302; 21: 10.2528; 23: 10.2528
Jabalpur | Dindori | Dindori | 181.56 | 14.5248 |  |  | 10.8936 |  | 3.6312 | 9: 3.6312; 11: 3.6312; 13: 21.7872; 15: 21.7872; 17: 27.234; 19: 27.234; 21: 23.6028; 23: 23.6028
Jabalpur | Jabalpur | Jabalpur-1 | 39.861 | 4.3847 |  |  | 1.1958 |  | 0.79722 | 9: 0.79722; 11: 0.79722; 13: 4.7833; 15: 4.7833; 17: 5.9791; 19: 5.9791; 21: 5.1819; 23: 5.1819
Jabalpur | Jabalpur | Jabalpur-2 | 52.606 | 4.2085 |  |  | 3.1564 |  | 1.0521 | 9: 1.0521; 11: 1.0521; 13: 6.3127; 15: 6.3127; 17: 7.8909; 19: 7.8909; 21: 6.8388; 23: 6.8388
Jabalpur | Katni | Katni | 44.213 | 3.537 |  |  | 2.6528 |  | 0.88426 | 9: 0.88426; 11: 0.88426; 13: 5.3056; 15: 5.3056; 17: 6.6319; 19: 6.6319; 21: 5.7477; 23: 5.7477
Jabalpur | Mandla | Mandla | 212.26 | 16.9808 |  |  | 12.7356 |  | 4.2452 | 9: 4.2452; 11: 4.2452; 13: 25.4712; 15: 25.4712; 17: 31.839; 19: 31.839; 21: 27.5938; 23: 27.5938
Jabalpur | Narsinghpur | Narsinghpur-1 | 47.605 | 3.8084 |  |  | 2.8563 |  | 0.9521 | 9: 0.9521; 11: 0.9521; 13: 5.7126; 15: 5.7126; 17: 7.1407; 19: 7.1407; 21: 6.1886; 23: 6.1886
Jabalpur | Narsinghpur | Narsinghpur-2 | 51.1 | 4.088 |  |  | 3.066 |  | 1.022 | 9: 1.022; 11: 1.022; 13: 6.132; 15: 6.132; 17: 7.665; 19: 7.665; 21: 6.643; 23: 6.643
Jabalpur | Seoni | Seoni-1 | 57.873 | 4.63 |  |  | 3.4724 |  | 1.1575 | 9: 1.1575; 11: 1.1575; 13: 6.9448; 15: 6.9448; 17: 8.6809; 19: 8.6809; 21: 7.5235; 23: 7.5235
Jabalpur | Seoni | Seoni-2 | 58.055 | 4.64 |  |  | 3.4833 |  | 1.1611 | 9: 1.1611; 11: 1.1611; 13: 6.9666; 15: 6.9666; 17: 8.7082; 19: 8.7082; 21: 7.5472; 23: 7.5472
Jabalpur | Seoni | Seoni-3
Shahdol | Anuppur | Anuppur | 157.27 | 12.5816 |  |  | 9.4362 |  | 3.1454 | 9: 3.1454; 11: 3.1454; 13: 18.8724; 15: 18.8724; 17: 23.5905; 19: 23.5905; 21: 20.4451; 23: 20.4451
Rewa | Baidhan | Baidhan-1 | 127.41 | 10.1928 |  |  | 7.6446 |  | 2.5482 | 9: 2.5482; 11: 2.5482; 13: 15.2892; 15: 15.2892; 17: 19.1115; 19: 19.1115; 21: 16.5633; 23: 16.5633
Rewa | Baidhan | Baidhan-2 | 117.376 | 9.3901 |  |  | 7.0426 |  | 2.3475 | 9: 2.3475; 11: 2.3475; 13: 14.0851; 15: 14.0851; 17: 17.6064; 19: 17.6064; 21: 15.2589; 23: 15.2589
Rewa | Rewa | Rewa-1 | 109.4 | 8.752 |  |  | 6.564 |  | 2.188 | 9: 2.188; 11: 2.188; 13: 13.128; 15: 13.128; 17: 16.41; 19: 16.41; 21: 14.222; 23: 14.222
Rewa | Rewa | Rewa-2 | 81.892 | 6.5514 |  |  | 4.9135 |  | 1.6378 | 9: 1.6378; 11: 1.6378; 13: 9.827; 15: 9.827; 17: 12.2838; 19: 12.2838; 21: 10.646; 23: 10.646
Rewa | Satna | Satna-1 | 56.219 | 4.4975 |  |  | 3.3731 |  | 1.1244 | 9: 1.1244; 11: 1.1244; 13: 6.7463; 15: 6.7463; 17: 8.4329; 19: 8.4329; 21: 7.3085; 23: 7.3085
Rewa | Satna | Satna-2 | 42.196 | 3.3757 |  |  | 2.5318 |  | 0.84392 | 9: 0.84392; 11: 0.84392; 13: 5.0635; 15: 5.0635; 17: 6.3294; 19: 6.3294; 21: 5.4855; 23: 5.4855
Shahdol | Shahdol | Shahdol | 194.39 | 15.5512 |  |  | 11.6634 |  | 3.8878 | 9: 3.8878; 11: 3.8878; 13: 23.3268; 15: 23.3268; 17: 29.1585; 19: 29.1585; 21: 25.2707; 23: 25.2707
Rewa | Sidhi | Sidhi | 95.252 | 7.6202 |  |  | 5.7151 |  | 1.905 | 9: 1.905; 11: 1.905; 13: 11.4302; 15: 11.4302; 17: 14.2878; 19: 14.2878; 21: 12.3828; 23: 12.3828
Shahdol | Umria | Umaria | 101.057 | 8.0846 |  |  | 6.0634 |  | 2.0211 | 9: 2.0211; 11: 2.0211; 13: 12.1268; 15: 12.1268; 17: 15.1586; 19: 15.1586; 21: 13.1374; 23: 13.1374
Sagar | Chhatarpur | Chhatarpur-1 | 84.97 | 6.7976 |  |  | 5.0982 |  | 1.6994 | 9: 1.6994; 11: 1.6994; 13: 10.1964; 15: 10.1964; 17: 12.7455; 19: 12.7455; 21: 11.0461; 23: 11.0461
Sagar | Chhatarpur | Chhatarpur-2 | 76.89 | 6.1512 |  |  | 4.6134 |  | 1.5378 | 9: 1.5378; 11: 1.5378; 13: 9.2268; 15: 9.2268; 17: 11.5335; 19: 11.5335; 21: 9.9957; 23: 9.9957
Sagar | Damoh | Damoh-1 | 20.51 | 1.6408 |  |  | 1.2306 |  | 0.4102 | 9: 0.4102; 11: 0.4102; 13: 2.4612; 15: 2.4612; 17: 3.0765; 19: 3.0765; 21: 2.6663; 23: 2.6663
Sagar | Damoh | Damoh-2 | 26.431 | 2.9074 |  |  | 0.79293 |  | 0.52862 | 9: 0.52862; 11: 0.52862; 13: 3.1717; 15: 3.1717; 17: 3.9646; 19: 3.9646; 21: 3.436; 23: 3.436
Sagar | Panna | Panna-1 | 81.425 | 6.514 |  |  | 4.8855 |  | 1.6285 | 9: 1.6285; 11: 1.6285; 13: 9.771; 15: 9.771; 17: 12.2137; 19: 12.2137; 21: 10.5853; 23: 10.5853
Sagar | Panna | Panna-2 | 72.475 | 5.798 |  |  | 4.3485 |  | 1.4495 | 9: 1.4495; 11: 1.4495; 13: 8.697; 15: 8.697; 17: 10.8712; 19: 10.8712; 21: 9.4217; 23: 9.4217
Sagar | Sagar | Sagar-1 | 91.07 | 7.2856 |  |  | 5.4642 |  | 1.8214 | 9: 1.8214; 11: 1.8214; 13: 10.9284; 15: 10.9284; 17: 13.6605; 19: 13.6605; 21: 11.8391; 23: 11.8391
Sagar | Sagar | Sagar-2 | 61.43 | 4.9144 |  |  | 3.6858 |  | 1.2286 | 9: 1.2286; 11: 1.2286; 13: 7.3716; 15: 7.3716; 17: 9.2145; 19: 9.2145; 21: 7.9859; 23: 7.9859
Sagar | Tikamgarh | Tikamgarh | 98.615 | 7.8892 |  |  | 5.9169 |  | 1.9723 | 9: 1.9723; 11: 1.9723; 13: 11.8338; 15: 11.8338; 17: 14.7923; 19: 14.7923; 21: 12.82; 23: 12.82
Ujjain | Dewas | Dewas-1 | 40.6 | 3.248 |  |  | 2.436 |  | 0.812 | 9: 0.812; 11: 0.812; 13: 4.872; 15: 4.872; 17: 6.09; 19: 6.09; 21: 5.278; 23: 5.278
Ujjain | Dewas | Dewas-2 | 25.907 | 2.8498 |  |  | 0.77721 |  | 0.51814 | 9: 0.51814; 11: 0.51814; 13: 3.1088; 15: 3.1088; 17: 3.8861; 19: 3.8861; 21: 3.3679; 23: 3.3679
Ujjain | Mandsour | Mandsour | 63.243 | 5.0594 |  |  | 3.7946 |  | 1.2649 | 9: 1.2649; 11: 1.2649; 13: 7.5892; 15: 7.5892; 17: 9.4864; 19: 9.4864; 21: 8.2216; 23: 8.2216
Ujjain | Neemuch | Neemuch | 14.529 | 4 |  |  | 1 |  |  | 13: 2; 15: 4; 17: 3.53
Ujjain | Ratlam | Ratlam | 2.23 | 2.23
Ujjain | Shajapur | Shajapur-1 | 47.3 | 3.784 |  |  | 2.838 |  | 0.946 | 9: 0.946; 11: 0.946; 13: 5.676; 15: 5.676; 17: 7.095; 19: 7.095; 21: 6.149; 23: 6.149
Ujjain | Agar | Agar | 26.192 | 2.8811 |  |  | 0.78576 |  | 0.52384 | 9: 0.52384; 11: 0.52384; 13: 3.143; 15: 3.143; 17: 3.9288; 19: 3.9288; 21: 3.405; 23: 3.405
Ujjain | Ujjain | Ujjain-1 | 27.519 | 3.0271 |  |  | 0.82557 |  | 0.55038 | 9: 0.55038; 11: 0.55038; 13: 3.3023; 15: 3.3023; 17: 4.1279; 19: 4.1279; 21: 3.5775; 23: 3.5775
Ujjain | Ujjain | Ujjain-2 | 8.715 | 4 |  |  | 2 |  |  | 13: 2.7

## Ag-2a
Agenda-R2(a)
Road wise review of Balance more than 4 yrs Old Works (PMGSY). As per OMMS
as on 31 May
CGM | District | PIU | Package No. | Year of Sanction | Date of Work Order (DDMMYY) | Name of Road | Length of Road (In Km) | Total Cost (Rs in Lacs) | Length completed (In Km) | Expenditure till date (Rs in Lacs) | Balance Length (In Km) | Balance Amount (Rs in Lacs) | Probable date of completion (DDMMYY) | Reason for non completion of road/Remarks

## Ag-2b
Agenda-R2(b)
Review of balance No. of works (more than 2 yrs & less than 4 yr )
CGM | District | PIU | Package No. | Year of Sanction | Date of Work Order (DDMMYY) | Name of Road | Length of Road (In Km) | Total Cost (Rs in Lacs) | Length completed (In Km) | Expenditure till date (Rs in Lacs) | Balance Length (In Km) | Balance Amount (Rs in Lacs) | Probable date of completion (DDMMYY) | Reason for non completion of road/Remarks

## Ag-2c(A)
Agenda-R2(c)
Review of balance work by no. of roads (less than 2 yrs )- PMGSY-I
CGM | District | PIU | Balance |  | Reason for non completion of work | Plan for Completion | [5 empty] | Remarks
No. Of works to be completed in
|  |  | No. Of Works | Length (In Km) |  | Jun'18 to Oct'18 | Nov'18 | Dec'18 | Jan'19 | Feb'19 | Mar'19
Indore | Alirajpur | Alirajpur
Shahdol | Anuppur | Anuppur
Gwalior | Ashoknagar | Ashoknagar-1
Gwalior | Ashoknagar | Ashoknagar-2
Rewa | Baidhan | Baidhan-1
Rewa | Baidhan | Baidhan-2
Jabalpur | Balaghat | Balaghat-1
Jabalpur | Balaghat | Balaghat-2
Indore | Barwani | Barwani
N'puram | Betul | Betul-1
N'puram | Betul | Betul-2
N'puram | Betul | Betul-3
Gwalior | Bhind | Bhind-1
Gwalior | Bhind | Bhind-2
Bhopal | Bhopal | Bhopal
Indore | Burhanpur | Burhanpur
Sagar | Chhatarpur | Chhatarpur-1
Sagar | Chhatarpur | Chhatarpur-2
Jabalpur | Chhindwara | Chhindwara-1
Jabalpur | Chhindwara | Chhindwara-2
Jabalpur | Chhindwara | Chhindwara-3
Sagar | Damoh | Damoh-1
Sagar | Damoh | Damoh-2
Gwalior | Datia | Datia
Ujjain | Dewas | Dewas-1
Ujjain | Dewas | Dewas-2
Indore | Dhar | Dhar-1
Indore | Dhar | Dhar-2
Indore | Dhar | Dhar-3
Jabalpur | Dindori | Dindori
Gwalior | Guna | Guna-1
Gwalior | Guna | Guna-2
Gwalior | Gwalior | Gwalior
N'puram | Harda | Harda
N'puram | Hoshangabad | Hoshangabad-2
Indore | Indore | Indore
Jabalpur | Jabalpur | Jabalpur-1
Jabalpur | Jabalpur | Jabalpur-2
Indore | Jhabua | Jhabua
Jabalpur | Katni | Katni
Indore | Khaggone | Khaggone-1
Indore | Khargone | Khargone-2
Indore | Khandwa | Khandwa
Jabalpur | Mandla | Mandla
Ujjain | Mandsour | Mandsour
Gwalior | Morena | Morena
Jabalpur | Narsinghpur | Narsinghpur-1
Jabalpur | Narsinghpur | Narsinghpur-2
Ujjain | Neemuch | Neemuch
Sagar | Panna | Panna-1
Sagar | Panna | Panna-2
Bhopal | Raisen | Raisen-1
Bhopal | Raisen | Raisen-2
Bhopal | Rajgarh | Rajgarh-1
Bhopal | Rajgarh | Rajgarh-2
Ujjain | Ratlam | Ratlam
Rewa | Rewa | Rewa-1
Rewa | Rewa | Rewa-2
Sagar | Sagar | Sagar-1
Sagar | Sagar | Sagar-2
Rewa | Satna | Satna-1
Rewa | Satna | Satna-2
Bhopal | Sehore | Sehore
Jabalpur | Seoni | Seoni-1
Jabalpur | Seoni | Seoni-2
Jabalpur | Seoni | Seoni-3
Gwalior | Seopur | Seopur
Shahdol | Shahdol | Shahdol
Ujjain | Shajapur | Shajapur-1
Gwalior | Shivpuri | Shivpuri-1
Gwalior | Shivpuri | Shivpuri-2
Ujjain | Agar | Agar
Rewa | Sidhi | Sidhi
Sagar | Tikamgarh | Tikamgarh
Ujjain | Ujjain | Ujjain-1
Ujjain | Ujjain | Ujjain-2
Shahdol | Umria | Umria
Bhopal | Vidisha | Vidisha-1
Bhopal | Vidisha | Vidisha-2

## Ag-2c(B)
Agenda-R2(c)
Review of balance work by no. of roads (less than 2 yrs )- PMGSY-II
CGM | District | PIU | Balance |  | Reason for non completion of work | Plan for Completion | [5 empty] | Remarks
No. Of works to be completed in
|  |  | No. Of Works | Length (In Km) |  | Jun'18 to Oct'18 | Nov'18 | Dec'18 | Jan'19 | Feb'19 | Mar'19
Indore | Alirajpur | Alirajpur
Shahdol | Anuppur | Anuppur
Gwalior | Ashoknagar | Ashoknagar-1
Gwalior | Ashoknagar | Ashoknagar-2
Rewa | Baidhan | Baidhan-1
Rewa | Baidhan | Baidhan-2
Jabalpur | Balaghat | Balaghat-1
Jabalpur | Balaghat | Balaghat-2
Indore | Barwani | Barwani
N'puram | Betul | Betul-1
N'puram | Betul | Betul-2
N'puram | Betul | Betul-3
Gwalior | Bhind | Bhind-1
Gwalior | Bhind | Bhind-2
Bhopal | Bhopal | Bhopal
Indore | Burhanpur | Burhanpur
Sagar | Chhatarpur | Chhatarpur-1
Sagar | Chhatarpur | Chhatarpur-2
Jabalpur | Chhindwara | Chhindwara-1
Jabalpur | Chhindwara | Chhindwara-2
Jabalpur | Chhindwara | Chhindwara-3
Sagar | Damoh | Damoh-1
Sagar | Damoh | Damoh-2
Gwalior | Datia | Datia
Ujjain | Dewas | Dewas-1
Ujjain | Dewas | Dewas-2
Indore | Dhar | Dhar-1
Indore | Dhar | Dhar-2
Indore | Dhar | Dhar-3
Jabalpur | Dindori | Dindori
Gwalior | Guna | Guna-1
Gwalior | Guna | Guna-2
Gwalior | Gwalior | Gwalior
N'puram | Harda | Harda
N'puram | Hoshangabad | Hoshangabad-2
Indore | Indore | Indore
Jabalpur | Jabalpur | Jabalpur-1
Jabalpur | Jabalpur | Jabalpur-2
Indore | Jhabua | Jhabua
Jabalpur | Katni | Katni
Indore | Khaggone | Khaggone-1
Indore | Khargone | Khargone-2
Indore | Khandwa | Khandwa
Jabalpur | Mandla | Mandla
Ujjain | Mandsour | Mandsour
Gwalior | Morena | Morena
Jabalpur | Narsinghpur | Narsinghpur-1
Jabalpur | Narsinghpur | Narsinghpur-2
Ujjain | Neemuch | Neemuch
Sagar | Panna | Panna-1
Sagar | Panna | Panna-2
Bhopal | Raisen | Raisen-1
Bhopal | Raisen | Raisen-2
Bhopal | Rajgarh | Rajgarh-1
Bhopal | Rajgarh | Rajgarh-2
Ujjain | Ratlam | Ratlam
Rewa | Rewa | Rewa-1
Rewa | Rewa | Rewa-2
Sagar | Sagar | Sagar-1
Sagar | Sagar | Sagar-2
Rewa | Satna | Satna-1
Rewa | Satna | Satna-2
Bhopal | Sehore | Sehore
Jabalpur | Seoni | Seoni-1
Jabalpur | Seoni | Seoni-2
Jabalpur | Seoni | Seoni-3
Gwalior | Seopur | Seopur
Shahdol | Shahdol | Shahdol
Ujjain | Shajapur | Shajapur-1
Gwalior | Shivpuri | Shivpuri-1
Gwalior | Shivpuri | Shivpuri-2
Ujjain | Agar | Agar
Rewa | Sidhi | Sidhi
Sagar | Tikamgarh | Tikamgarh
Ujjain | Ujjain | Ujjain-1
Ujjain | Ujjain | Ujjain-2
Shahdol | Umria | Umria
Bhopal | Vidisha | Vidisha-1
Bhopal | Vidisha | Vidisha-2

## ag-2d
Agenda R2(d)
Progress of Review of RCTRC & RRNMU's
S.No | Name of Building | Particulars of Works | Work Order |  | Total Cost (Rs in Lacs) | Expenditure till 31st May 18 (Rs in Lacs) | Stipulated date of Completion (DDMMYY) | Progress Status | Expected Date of Completion (DDMMYY) | Remarks
|  |  | No. | Date (DDMMYY)
1 | RCTRC Walmi Bhopal | Construction of building work (RCTRC 01) | 1062 | 29-06-2015 | 680.69
|  | Interior/Fire fighting etc work (RCTRC 02) | 1255 | 2017-03-11 | 88.93
|  | ELV system/gadgets etc work (RCTRC 03) | 1253 | 2017-03-11 | 43.59
|  | Lancscaping etc work (RCTRC 04) | 1249 | 31-10-2017 | 101.27
|  | External electrification work (RCTRC 05) | 1277 | 2017-07-11 | 41.38
|  | Furniture in Admin. building work (RCTRC 06) | 1389 | 2017-04-12 | 66.81
|  | Furniture in Guest house and Hostel work (RCTRC 07) | 1387 | 2017-04-12 | 52.19
|  | Solar Panel work (RCTRC 08) | 1443 | 22-12-2017 | 25.2
|  | CC approach road (RCTRC 09) | 1414 | 14-12-2017 | 27.14
2 | RRNMU Bhopal

## Ag-3a
Progress of State Connectivity / State Mandi Works | [18 empty] | Agenda- R3(a)
CGM | District | PIU | State Connectivity | [8 empty] | State Mandi
|  |  | Sanctions |  |  | Completion |  |  | Balance |  |  | Sanctions |  |  | Completion |  |  | Balance
|  |  | No. Of Works | Length (In Km) | Amount (Rs in Lacs) | No. Of Works | Length (In Km) | Expenditure (Rs in Lacs) | No. Of Works | Length (In Km) | Amount (Rs in Lacs) | No. Of Works | Length (In Km) | Amount (Rs in Lacs) | No. Of Works | Length (In Km) | Expenditure (Rs in Lacs) | No. Of Works | Length (In Km) | Amount (Rs in Lacs)
N'puram | Betul | Betul-1
N'puram | Betul | Betul-2
N'puram | Betul | Betul-3
N'puram | Harda | Harda
N'puram | Hoshangabad | Hoshangabad
N'Puram Total
Bhopal | Bhopal | Bhopal
Bhopal | Raisen | Raisen-1
Bhopal | Raisen | Raisen-2
Bhopal | Rajgarh | Rajgarh-1
Bhopal | Rajgarh | Rajgarh-2
Bhopal | Sehore | Sehore
Bhopal | Vidisha | Vidisha-1
Bhopal | Vidisha | Vidisha-2
Bhopal Total
Gwalior | Ashok Nagar | AshokNagar-1
Gwalior | Ashok Nagar | AshokNagar-2
Gwalior | Bhind | Bhind-1
Gwalior | Bhind | Bhind-2
Gwalior | Datia | Datia
Gwalior | Guna | Guna-1
Gwalior | Guna | Guna-2
Gwalior | Gwalior | Gwalior
Gwalior | Morena | Morena
Gwalior | Seopur | Seopur
Gwalior | Shivpuri | Shivpuri-1
Gwalior | Shivpuri | Shivpuri-2
Gwalior Total
Indore | Alirajpur | Alirajpur
Indore | Barwani | Barwani-1
Indore | Burhanpur | Burhanpur
Indore | Dhar | Dhar-1
Indore | Dhar | Dhar-2
Indore | Dhar | Dhar-3
Indore | Indore | Indore
Indore | Jhabua | Jhabua
Indore | Khandwa | Khandwa
Indore | Khargone | Khargone-1
Indore | Khargone | Khargone-2
Indore Total
Jabalpur | Balaghat | Balaghat-1
Jabalpur | Balaghat | Balaghat-2
Jabalpur | Chhindwara | Chhindwara-1
Jabalpur | Chhindwara | Chhindwara-2
Jabalpur | Dindori | Dindori
Jabalpur | Jabalpur | Jabalpur-1
Jabalpur | Jabalpur | Jabalpur-2
Jabalpur | Katni | Katni
Jabalpur | Mandla | Mandla
Jabalpur | Narsighpur | Narsighpur-1
Jabalpur | Narsighpur | Narsighpur-2
Jabalpur | Seoni | Seoni-1
Jabalpur | Seoni | Seoni-2
Jabalpur Total
Rewa/Shahdol | Anuppur | Anuppur
Rewa/Shahdol | Rewa | Rewa-1
Rewa/Shahdol | Rewa | Rewa-2
Rewa/Shahdol | Satna | Satna-1
Rewa/Shahdol | Satna | Satna-2
Rewa/Shahdol | Shahdol | Shahdol
Rewa/Shahdol | Sidhi | Sidhi
Rewa/Shahdol | Singrauli | Singrauli-1
Rewa/Shahdol | Singrauli | Singrauli-2
Rewa/Shahdol | Umaria | Umaria
Rewa/Shahdol Total
Sagar | Chhatarpur | Chhatarpur-1
Sagar | Chhatarpur | Chhatarpur-2
Sagar | Damoh | Damoh-1
Sagar | Damoh | Damoh-2
Sagar | Panna | Panna-1
Sagar | Panna | Panna-2
Sagar | Sagar | Sagar-1
Sagar | Sagar | Sagar-2
Sagar | Tikamgarh | Tikamgarh
Sagar Total
Ujjain | Dewas | Dewas-1
Ujjain | Dewas | Dewas-2
Ujjain | Mandsour | Mandsour
Ujjain | Neemuch | Neemuch
Ujjain | Ratlam | Ratlam
Ujjain | Shajapur | Shajapur-1
Ujjain | Shajapur | Shajapur-2
Ujjain | Ujjain | Ujjain-1
Ujjain | Ujjain | Ujjain-2
Ujjain Total
Grand Total

## Ag-3b_
Progress of MPRCP & X Category Works | [18 empty] | Agenda- R3(b)
CGM | District | PIU | MPRCP | [8 empty] | X-Category
|  |  | Sanctions |  |  | Completion |  |  | Balance |  |  | Sanctions |  |  | Completion |  |  | Balance
|  |  | No. Of Works | Length (In Km) | Amount (Rs in Lacs) | No. Of Works | Length (In Km) | Expenditure (Rs in Lacs) | No. Of Works | Length (In Km) | Amount (Rs in Lacs) | No. Of Works | Length (In Km) | Amount (Rs in Lacs) | No. Of Works | Length (In Km) | Expenditure (Rs in Lacs) | No. Of Works | Length (In Km) | Amount (Rs in Lacs)
N'puram | Betul | Betul-1
N'puram | Betul | Betul-2
N'puram | Betul | Betul-3
N'puram | Harda | Harda
N'puram | Hoshangabad | Hoshangabad
N'Puram Total
Bhopal | Bhopal | Bhopal
Bhopal | Raisen | Raisen-1
Bhopal | Raisen | Raisen-2
Bhopal | Rajgarh | Rajgarh-1
Bhopal | Rajgarh | Rajgarh-2
Bhopal | Sehore | Sehore
Bhopal | Vidisha | Vidisha-1
Bhopal | Vidisha | Vidisha-2
Bhopal Total
Gwalior | Ashok Nagar | AshokNagar-1
Gwalior | Ashok Nagar | AshokNagar-2
Gwalior | Bhind | Bhind-1
Gwalior | Bhind | Bhind-2
Gwalior | Datia | Datia
Gwalior | Guna | Guna-1
Gwalior | Guna | Guna-2
Gwalior | Gwalior | Gwalior
Gwalior | Morena | Morena
Gwalior | Seopur | Seopur
Gwalior | Shivpuri | Shivpuri-1
Gwalior | Shivpuri | Shivpuri-2
Gwalior Total
Indore | Alirajpur | Alirajpur
Indore | Barwani | Barwani-1
Indore | Burhanpur | Burhanpur
Indore | Dhar | Dhar-1
Indore | Dhar | Dhar-2
Indore | Dhar | Dhar-3
Indore | Indore | Indore
Indore | Jhabua | Jhabua
Indore | Khandwa | Khandwa
Indore | Khargone | Khargone-1
Indore | Khargone | Khargone-2
Indore Total
Jabalpur | Balaghat | Balaghat-1
Jabalpur | Balaghat | Balaghat-2
Jabalpur | Chhindwara | Chhindwara-1
Jabalpur | Chhindwara | Chhindwara-2
Jabalpur | Dindori | Dindori
Jabalpur | Jabalpur | Jabalpur-1
Jabalpur | Jabalpur | Jabalpur-2
Jabalpur | Katni | Katni
Jabalpur | Mandla | Mandla
Jabalpur | Narsighpur | Narsighpur-1
Jabalpur | Narsighpur | Narsighpur-2
Jabalpur | Seoni | Seoni-1
Jabalpur | Seoni | Seoni-2
Jabalpur Total
Rewa/Shahdol | Anuppur | Anuppur
Rewa/Shahdol | Rewa | Rewa-1
Rewa/Shahdol | Rewa | Rewa-2
Rewa/Shahdol | Satna | Satna-1
Rewa/Shahdol | Satna | Satna-2
Rewa/Shahdol | Shahdol | Shahdol
Rewa/Shahdol | Sidhi | Sidhi
Rewa/Shahdol | Singrauli | Singrauli-1
Rewa/Shahdol | Singrauli | Singrauli-2
Rewa/Shahdol | Umaria | Umaria
Rewa/Shahdol Total
Sagar | Chhatarpur | Chhatarpur-1
Sagar | Chhatarpur | Chhatarpur-2
Sagar | Damoh | Damoh-1
Sagar | Damoh | Damoh-2
Sagar | Panna | Panna-1
Sagar | Panna | Panna-2
Sagar | Sagar | Sagar-1
Sagar | Sagar | Sagar-2
Sagar | Tikamgarh | Tikamgarh
Sagar Total
Ujjain | Dewas | Dewas-1
Ujjain | Dewas | Dewas-2
Ujjain | Mandsour | Mandsour
Ujjain | Neemuch | Neemuch
Ujjain | Ratlam | Ratlam
Ujjain | Shajapur | Shajapur-1
Ujjain | Shajapur | Shajapur-2
Ujjain | Ujjain | Ujjain-1
Ujjain | Ujjain | Ujjain-2
Ujjain Total
Grand Total

## Ag-3c
Agenda-R3(c)
Review of balance works of State Connectivity (more than 2 yrs)
CGM | District | PIU | Package No. | Year of Sanction | Date of Work Order (DDMMYY) | Name of Road | Length of Road (In Km) | Total Cost (Rs in Lacs) | Length completed (In Km) | Expenditure till date (Rs in Lacs) | Balance Length (In Km) | Balance Amount (Rs in Lacs) | Probable date of completion (DDMMYY) | Reason for non completion of road/Remarks

## Ag-4a
Agenda-R4(a)
Progress Review of UPG Works
S.No. | Division | PIU | Sanction Work |  |  | Completed Work |  |  | Balance Work
|  |  | No. of works | Length (In Km) | Total contract amount (Rs in Lacs) | No. of works | Length (In Km) | Total amount paid (Rs in Lacs) | No. of works | Length (In Km) | Total Balance amount (Rs in Lacs)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12

## Ag-4b
Agenda-R4(b)
Review of balance works of Upgradation (more than 2 yrs)
CGM | District | PIU | Package No. | Year of Sanction | Date of Work Order (DDMMYY) | Name of Road | Length of Road (In Km) | Total Cost (Rs in Lacs) | Length completed (In Km) | Expenditure till date (Rs in Lacs) | Balance Length (In Km) | Balance Amount (Rs in Lacs) | Probable date of completion (DDMMYY) | Reason for non completion of road/Remarks

## Ag-5
Agenda-R5
Progress of all kinds of Bridges
CGM | District | PIU | Schemes (PMGSY1/PMGSY2/SC/SM/MPRCP) | Package Number | No. Of Bridge in Package | Package Cost (Rs in Lacs) | Date of Work Order (DDMMYY) | No. Of Bridge | Total Expenditure made as on 31st May 18 (Rs in Lacs) | Balance Amount (Rs in Lacs) | Progress Status | Completion Plan for 18-19 | Probable date of completion for balance Incomplete bridges After March-19
N'puram | Betul | Betul-1
N'puram | Betul | Betul-2
N'puram | Betul | Betul-3
N'puram | Harda | Harda
N'puram | Hoshangabad | Hoshangabad
N'Puram Total
Bhopal | Bhopal | Bhopal
Bhopal | Raisen | Raisen-1
Bhopal | Raisen | Raisen-2
Bhopal | Rajgarh | Rajgarh-1
Bhopal | Rajgarh | Rajgarh-2
Bhopal | Sehore | Sehore
Bhopal | Vidisha | Vidisha-1
Bhopal | Vidisha | Vidisha-2
Bhopal Total
Gwalior | Ashok Nagar | AshokNagar-1
Gwalior | Ashok Nagar | AshokNagar-2
Gwalior | Bhind | Bhind-1
Gwalior | Bhind | Bhind-2
Gwalior | Datia | Datia
Gwalior | Guna | Guna-1
Gwalior | Guna | Guna-2
Gwalior | Gwalior | Gwalior
Gwalior | Morena | Morena
Gwalior | Seopur | Seopur
Gwalior | Shivpuri | Shivpuri-1
Gwalior | Shivpuri | Shivpuri-2
Gwalior Total
Indore | Alirajpur | Alirajpur
Indore | Barwani | Barwani-1
Indore | Burhanpur | Burhanpur
Indore | Dhar | Dhar-1
Indore | Dhar | Dhar-2
Indore | Dhar | Dhar-3
Indore | Indore | Indore
Indore | Jhabua | Jhabua
Indore | Khandwa | Khandwa
Indore | Khargone | Khargone-1
Indore | Khargone | Khargone-2
Indore Total
Jabalpur | Balaghat | Balaghat-1
Jabalpur | Balaghat | Balaghat-2
Jabalpur | Chhindwara | Chhindwara-1
Jabalpur | Chhindwara | Chhindwara-2
Jabalpur | Dindori | Dindori
Jabalpur | Jabalpur | Jabalpur-1
Jabalpur | Jabalpur | Jabalpur-2
Jabalpur | Katni | Katni
Jabalpur | Mandla | Mandla
Jabalpur | Narsighpur | Narsighpur-1
Jabalpur | Narsighpur | Narsighpur-2
Jabalpur | Seoni | Seoni-1
Jabalpur | Seoni | Seoni-2
Jabalpur Total
Rewa/Shahdol | Anuppur | Anuppur
Rewa/Shahdol | Rewa | Rewa-1
Rewa/Shahdol | Rewa | Rewa-2
Rewa/Shahdol | Satna | Satna-1
Rewa/Shahdol | Satna | Satna-2
Rewa/Shahdol | Shahdol | Shahdol
Rewa/Shahdol | Sidhi | Sidhi
Rewa/Shahdol | Singrauli | Singrauli-1
Rewa/Shahdol | Singrauli | Singrauli-2
Rewa/Shahdol | Umaria | Umaria
Rewa/Shahdol Total
Sagar | Chhatarpur | Chhatarpur-1
Sagar | Chhatarpur | Chhatarpur-2
Sagar | Damoh | Damoh-1
Sagar | Damoh | Damoh-2
Sagar | Panna | Panna-1
Sagar | Panna | Panna-2
Sagar | Sagar | Sagar-1
Sagar | Sagar | Sagar-2
Sagar | Tikamgarh | Tikamgarh
Sagar Total
Ujjain | Dewas | Dewas-1
Ujjain | Dewas | Dewas-2
Ujjain | Mandsour | Mandsour
Ujjain | Neemuch | Neemuch
Ujjain | Ratlam | Ratlam
Ujjain | Shajapur | Shajapur-1
Ujjain | Shajapur | Shajapur-2
Ujjain | Ujjain | Ujjain-1
Ujjain | Ujjain | Ujjain-2
Ujjain Total
Grand Total

## Ag-6
Agenda-R6
Status of DPR preparation for bridges on roads sanctioned before 2011
Division | District | PIU | DPR Status of Pre 2011 Sanctioned roads |  |  |  | if delayed give reason | Probable date of preparation of DPR | Probable date of STA
|  |  | Bridges (15-60 meters) |  | Bridges (more than 60 meters)
|  |  | No. Of bridge DPR to be prepared | DPR prepared | To be prepared | DPR prepared

## Ag-7
R-7
Maintenace Drive
S. No | CGM | District | PIU | Total Number of Road Under Maintenance |  |  |  | Maintenance status of Road as on Today |  |  |  |  | Detailed reason for Fair and Poor | No. of Roads for wihich SCN is issued to contra-ctor | No. of Roads for wihich contract has been termin-ated | Remark
|  |  |  | Within 5 Year | MTN | PTN | Total | Excell-ent | Good | Fair | Poor | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17

## Ag-8
R-8
Informatrion Regarding Post 10 Year Maintenance Packages in eMarg
S.No. | CGM | District | PIU | No. of Sanctioned Post 10 Packages (AA Issued) | No. of packages for which work order have been issued | No. of Post 10 Packages created on E-Marg Portal | Remainning Packages pending for creation on on E-Marg Portal
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 (5-7)
1 | Jabalpur | Balaghat | Balaghat 1 | 27
Balaghat 2
|  | Chhindwara | Chhindwara 1 | 28
Chhindwara 2
|  | Dindori | Dindori | 11
|  | Jabalpur | Jabalpur 1 | 14
Jabalpur 2
|  | Katni | Katni | 9
|  | Mandla | Mandla | 12
|  | Narsinghpur | Narsinghpur 1 | 8
Narsinghpur 2
|  | Seoni | Seoni 1 | 11
Seoni 2
120
2 | Bhopal | Bhopal | Bhopal | 4
|  | Raisen | Raisen 1 | 19
Raisen 2
|  | Rajgarh | Rajgarh 1 | 17
Rajgarh 2
|  | Sehore | Sehore | 13
|  | Vidisha | Vidisha 1 | 16
Vidisha 2
|  | Betul | Betul 1 | 39
Betul 2
|  | Harda | Harda | 3
|  | Hoshangabad | Hoshangabad 1 | 11
Hoshangabad 2
122
3 | Gwalior | Morena | Morena | 27
|  | Sheopur | Sheopur | 6
|  | Bhind | Bhind | 9
|  | Gwalior | Gwalior | 4
|  | Ashoknagar | Ashoknagar 1 | 5
Ashoknagar 2
|  | Shivpuri | Shivpuri 1 | 24
Shivpuri 2
|  | Datia | Datia | 11
|  | Guna | Guna 1 | 11
Guna 2
97
4 | Indore | Alirajpur | Alirajpur | 9
|  | Barwani | Barwani | 18
|  | Burhanpur | Burhanpur | 1
|  | Indore | Indore | 6
|  | Dhar | Dhar 1 | 22
Dhar 2
Dhar 3
|  | Jhabua | Jhabua | 12
|  | Khandwa | Khandwa | 17
|  | Khargone | Khargone 1 | 19
Khargone 2
104
6 | Rewa | Rewa | Rewa 1 | 22
Rewa 2
|  | Satna | Satna 1 | 14
Satna 2
|  | Sidhi | Sidhi | 12
|  | Singrauli | Waidhan 1 | 6
Waidhan 2
|  | Anuppur | Anuppur | 4
|  | Shahdol | Shahdol | 8
|  | Umaria | Umaria | 7
73
7 | Ujjian | Dewas | Dewas 1 | 12
Dewas 2
|  | Mandsaur | Mandsaur | 10
|  | Neemuch | Neemuch | 8
|  | Ratlam | Ratlam | 11
|  | Shajapur | Shajapur 1 | 17
Shajapur 2
|  | Ujjain | Ujjain 1 | 13
Ujjain 2
71
8 | Sagar | Chhatarpur | Chhatarpur | 7
|  | Damoh | Damoh | 13
|  | Panna | Panna 1 | 3
Panna 2
|  | Sagar | Sagar 1 | 20
Sagar 2
|  | Tikamgarh | Tikamgarh | 7
50
Grand Total |  |  |  | 637

## Ag-8a
R-8a
Packages where DLP Period Ended but MTN Tenders not Issued and MTN Period Ended but PTN Tender not Issued and Advance Planning
CGM | District | PIU | Maintenance Category | Road Without Agency (As on 31 May 2018) |  |  |  | Advance planning for roads( Maintenance period ending from 01.06.2018 to 31.08.2018)
| District | PIU |  | Total No. of Roads Without Agency | No of Roads for which estimates are being prepared | No of Roads for which estimates submitted to CGM for TS | No of Roads at AS/NIT level | Total No. of Roads | No of Roads for which estimates are being prepared | No of Roads for which estimates submitted to CGM for TS | No of Roads at AS/NIT level | Remark
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Bhopal | Betul | Betul-1 | Within DLP
Post 5 Year Maintenance
Post 10 Year Maintenance
|  | Betul-2 | Within DLP
Post 5 Year Maintenance
Post 10 Year Maintenance
| Betul | Betul-3 | Within DLP
Post 5 Year Maintenance
Post 10 Year Maintenance
| Bhopal | Bhopal | Within DLP
Post 5 Year Maintenance
Post 10 Year Maintenance
| Harda | Harda | Within DLP
Post 5 Year Maintenance
Post 10 Year Maintenance
| Hoshangabad | Hoshangabad-1 | Within DLP
Post 5 Year Maintenance
Post 10 Year Maintenance
|  | Hoshangabad-2 | Within DLP
Post 5 Year Maintenance
Post 10 Year Maintenance
| Raisen | Raisen-1 | Within DLP
Post 5 Year Maintenance
Post 10 Year Maintenance
|  | Raisen-2 | Within DLP
Post 5 Year Maintenance
Post 10 Year Maintenance
| Rajgarh | Rajgarh-1 | Within DLP
Post 5 Year Maintenance
Post 10 Year Maintenance
|  | Rajgarh-2 | Within DLP
Post 5 Year Maintenance
Post 10 Year Maintenance
| Sehore | Sehore | Within DLP
Post 5 Year Maintenance
Post 10 Year Maintenance
| Vidisha | Vidisha-1 | Within DLP
Post 5 Year Maintenance
Post 10 Year Maintenance
|  | Vidisha-2 | Within DLP
Post 5 Year Maintenance
Post 10 Year Maintenance

## Ag-8b
Maintenace Drive | [13 empty] | Agenda R8(b)
S.No | CGM | District | PIU | Total Number of Road Under Maintenance |  |  |  | Maintenance status of Road as on Today |  |  |  |  | Reason for Fair and Poor | Remark
|  |  |  | Within 5 Year | MTN | PTN | Total | Excellent | Good | Fair | Poor | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 18 | 19 | 20 | 21 | 22 | 23 | 26

## Ag-9
Agenda-R9
Review of Pending Crust revision, Deviations, Change of alignment, Deletion cases.
Division | District | PIU | Name of Road/Bridge | Package No. | Type of Case | Year of Sanction | Sanctioned Length (In Km) | Total cost of road (Rs in Lacs) | Date from which Proposal is pending at (DDMMYY) |  |  | Remarks
[9 empty] | At PIU | At CGM | At HQ
Crust revision
Deviation
Change of alignment
Deletion

## Ag-10a
Agenda- R10(a)
Progress review of Pending final bill and LD cases.
Division | District | PIU | No of Packages pending for LD |  |  | No of cases Disposed by CGM | Remarks
|  |  | At PIU level | At CGM level | Total

## Ag-10 b
Agenda-R10(b)
Progress of pending financial closures for which final bills paid/Pending final bills
Division | District | PIU | Package No. | Date of CC (DDMMYY) | Date of Payment of Final Bill (DDMMYY) | Reason for delay | If final Bills paid than Probable date of Financial Closure on OMMS (DDMMYY)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| Alirajpur |  | MP1936
| Alirajpur |  | MP4923
| Alirajpur |  | MP4931
| Alirajpur |  | MP4932
| Alirajpur |  | MP4935
| Anuppur |  | MP46BRG001
| Ashok Nagar |  | MP47102
| Ashok Nagar |  | MP4733
| Ashok Nagar |  | MP-47509
| Ashok Nagar |  | MP-47516
| Ashok Nagar |  | MP4767
| Ashok Nagar |  | MP4789
| Balaghat |  | MP01225
| Barwani |  | MP02-100
| Barwani |  | MP0228
| Barwani |  | MP0250
| Barwani |  | MP0296
| Barwani |  | MP0298
| Barwani |  | MP2112
| Barwani |  | MP2113
| Betul |  | MP03246
| Betul |  | MP03254
| Betul |  | MP03257
| Betul |  | MP03267
| Betul |  | MP03502
| Betul |  | MP3B015
| Betul |  | MP3B016
| Bhind |  | MP0459
| Bhind |  | MP0469
| Bhind |  | MP0470
| Bhind |  | MP0473
| Bhind |  | MP0486
| Bhind |  | MP0487
| Bhopal |  | MP05-506
| Bhopal |  | MP05-511
| Bhopal |  | MP534
| Chhatarpur |  | MP06-505
| Chhatarpur |  | MP0677
| Chhatarpur |  | MP0680
| Chhatarpur |  | MP0685
| Chhatarpur |  | MP0694
| Chhindwara |  | MP07134
| Chhindwara |  | MP-07-192
| Chhindwara |  | MP07227
| Chhindwara |  | MP07232
| Chhindwara |  | MP07234
| Chhindwara |  | MP07243
| Chhindwara |  | MP07244
| Chhindwara |  | MP07253
| Chhindwara |  | MP07254
| Chhindwara |  | MP07258
| Chhindwara |  | MP07262
| Chhindwara |  | MP07264
| Chhindwara |  | MP07265
| Chhindwara |  | MP07275
| Chhindwara |  | MP07GB256
| Chhindwara |  | MP07GB266
| Chhindwara |  | MP7174
| Damoh |  | MP0844
| Damoh |  | MP0845
| Damoh |  | MP0847
| Damoh |  | MP0850
| Damoh |  | MP0856
| Damoh |  | MP0857
| Damoh |  | MP0858
| Datia |  | MP0924
| Datia |  | MP0929
| Datia |  | MP0946
| Datia |  | MP933
| Datia |  | MP939
| Datia |  | MP941
| Datia |  | MP942
| Datia |  | MP943
| Datia |  | MP944
| Dewas |  | MP10101
| Dewas |  | MP10110
| Dewas |  | MP10111
| Dewas |  | MP10114
| Dewas |  | MP-10-506
| Dewas |  | MP1073
| Dewas |  | MP1078
| Dewas |  | MP1082
| Dewas |  | MP1092
| Dewas |  | MP10B011
| Dewas |  | MP10B012
| Dewas |  | MP10B021
| Dhar |  | MP11121
| Dhar |  | MP11130
| Dhar |  | MP11144
| Dhar |  | MP11164
| Dhar |  | MP11170
| Dhar |  | MP11185
| Dhar |  | MP11186
| Dhar |  | MP11187
| Dhar |  | MP11188
| Dhar |  | MP11192
| Dhar |  | MP11194
| Dhar |  | MP11198
| Dhar |  | MP11B21
| Guna |  | MP13107
| Guna |  | MP13108
| Guna |  | MP13109
| Guna |  | MP13110
| Guna |  | MP13112
| Guna |  | MP13114
| Guna |  | MP13117
| Guna |  | MP13119
| Guna |  | MP13129
| Guna |  | MP13130
| Guna |  | MP13132
| Guna |  | MP13133
| Guna |  | MP13512
| Guna |  | MP1371
| Guna |  | MP1381
| Gwalior |  | MP1428
| Gwalior |  | MP1432
| Gwalior |  | MP1434
| Gwalior |  | MP1437
| Gwalior |  | MP1438
| Gwalior |  | MP1441
| Gwalior |  | MP1442
| Gwalior |  | MP1443
| Gwalior |  | MP1444
| Gwalior |  | MP1446
| Gwalior |  | MP1452
| Gwalior |  | MP1459
| Gwalior |  | MP14B04
| Hoshangabad |  | MP16100
| Hoshangabad |  | MP16101
| Hoshangabad |  | MP16103
| Hoshangabad |  | MP1689
| Hoshangabad |  | MP1692
| Hoshangabad |  | MP1694
| Indore |  | MP1731
| Indore |  | MP1735
| Indore |  | MP17515
| Indore |  | MP17517
| Indore |  | MP17518
| Jabalpur |  | MP1849
| Jabalpur |  | MP1866
| Jabalpur |  | MP1873
| Jabalpur |  | MP18B02
| Jabalpur |  | MP19B11
| Jhabua |  | MP19123
| Jhabua |  | MP19141
| Katni |  | MP2040
| Katni |  | MP2041
| Katni |  | MP2045
| Katni |  | MP2049
| Katni |  | MP-20-504
| Katni |  | MP20511
| Katni |  | MP2063
| Katni |  | MP2065
| Katni |  | MP2071
| Katni |  | MP2076
| Khandwa |  | MP21111
| Khandwa |  | MP21112
| Khandwa |  | MP21118
| Khandwa |  | MP21B06
| Khandwa |  | MP21B07
| Khandwa |  | MP21B08
| Khandwa |  | MP21B16
| Khandwa |  | MP21B17
| Khandwa |  | MP21B20
| Khandwa |  | MP21B22
| Khandwa |  | MP21B23
| Khandwa |  | MP21B24
| Khandwa |  | MP21B25
| Khandwa |  | MP21B26
| Khargone |  | MP22189
| Khargone |  | MP22191
| Mandla |  | MP2383
| Mandla |  | MP23-I-76
| Mandsour |  | MP2464
| Mandsour |  | MP2465
| Morena |  | MP2589
| Narsighpur |  | MP26105
| Narsighpur |  | MP26108
| Narsighpur |  | MP26121
| Narsighpur |  | MP2688
| Panna |  | MP2861
| Panna |  | MP2874
| Panna |  | MP2882
| Panna |  | MP2884
| Panna |  | MP2886
| Panna |  | MP2894
| Raisen |  | MP29129
| Raisen |  | MP29133
| Raisen |  | MP29141
| Raisen |  | MP29143
| Raisen |  | MP29147
| Raisen |  | MP29148
| Raisen |  | MP29149
| Raisen |  | MP29151
| Raisen |  | MP29155
| Raisen |  | MP29156
| Raisen |  | MP29158
| Raisen |  | MP29160
| Raisen |  | MP29161
| Raisen |  | MP29166
| Raisen |  | MP29168
| Rajgarh |  | MP30102
| Rajgarh |  | MP30104
| Rajgarh |  | MP30111
| Rajgarh |  | MP3090
| Rajgarh |  | MP3092
| Rajgarh |  | MP3098
| Ratlam |  | MP31102
| Rewa |  | MP32112
| Rewa |  | MP32130
| Rewa |  | MP32134
| Rewa |  | MP32135
| Rewa |  | MP32150
| Rewa |  | MP32151
| Rewa |  | MP32152
| Rewa |  | MP32158
| Rewa |  | MP32160
| Rewa |  | MP32163
| Sagar |  | MP33102
| Sagar |  | MP33110
| Sagar |  | MP33124
| Sagar |  | MP33130
| Sagar |  | MP33510
| Sagar |  | MP3362
| Sagar |  | MP3396
| Sagar |  | MP33B11
| Satna |  | MP34111
| Satna |  | MP34112
| Sehore |  | MP35B04
| Seoni |  | MP36147
| Seoni |  | MP36155
| Seoni |  | MP36157
| Seoni |  | MP36160
| Seoni |  | MP36180
| Seoni |  | MP36184
| Seoni |  | MP36190
| Seoni |  | MP36204
| Seoni |  | MP36210
| Seoni |  | MP36501
| Seoni |  | MP3676
| Seoni |  | MP36B01
| Seoni |  | MP36GB209
| Seoni |  | MP36-I-118
| Seoni |  | MP36-I-124
| Seopur |  | MP3714
| Seopur |  | MP3721
| Seopur |  | MP3731
| Seopur |  | MP3733
| Shahdol |  | MP38108
| Shahdol |  | MP38109
| Shahdol |  | MP38112
| Shahdol |  | MP38113
| Shahdol |  | MP38-I-87
| Shajapur |  | MP39106
| Shajapur |  | MP39108
| Agar |  | MP39112
| Agar |  | MP39124
| Shajapur |  | MP39125
| Shivpuri |  | MP40104
| Shivpuri |  | MP40109
| Shivpuri |  | MP40111
| Shivpuri |  | MP40119
| Shivpuri |  | MP40121
| Sidhi |  | MP41199
| Sidhi |  | MP41201
| Singrauli |  | MP5035
| Singrauli |  | MP5037
| Singrauli |  | MP5039
| Singrauli |  | MP5042
| Singrauli |  | MP5043
| Singrauli |  | MP5048
| Tikamgarh |  | MP4250
| Ujjain |  | MP43109
| Ujjain |  | MP43123
| Ujjain |  | MP43125
| Ujjain |  | MP43126
| Ujjain |  | MP43127
| Ujjain |  | MP43128
| Ujjain |  | MP43129
| Ujjain |  | MP43130
| Ujjain |  | MP43131
| Ujjain |  | MP43132
| Ujjain |  | MP43133
| Ujjain |  | MP43134
| Ujjain |  | MP43136
| Ujjain |  | MP43138
| Ujjain |  | MP43139
| Ujjain |  | MP43140
| Ujjain |  | MP43145
| Ujjain |  | MP43151
| Ujjain |  | MP43152
| Ujjain |  | MP43153
| Ujjain |  | MP43154
| Ujjain |  | MP43155
| Ujjain |  | MP43159
| Ujjain |  | MP-43520
| Ujjain |  | MP-43521
| Ujjain |  | MP-43522
| Ujjain |  | MP43525
| Ujjain |  | MP4379
| Umria |  | MP-44503
| Umria |  | MP-44506
| Umria |  | MP-4462
| Vidisha |  | MP4542
| Vidisha |  | MP4543
| Vidisha |  | MP4546
| Vidisha |  | MP4547
| Vidisha |  | MP4548
| Vidisha |  | MP4549
| Vidisha |  | MP45502
| Vidisha |  | MP45509
| Vidisha |  | MP45510
| Vidisha |  | MP4574
| Vidisha |  | MP4577
| Vidisha |  | MP4581
| Vidisha |  | MP4582
| Vidisha |  | MP4583
| Vidisha |  | MP4585
| Vidisha |  | MP4586
| Vidisha |  | MP4590

## Ag-11
Agenda-R11
Pending NQM ATRs as on 31.05.2018
S.No. | CGM | District | Name of Road | Pending ATR |  |  |  | Pending Since | Probable date of rectification by PIU | Remarks
|  |  |  | Ongoing / Complete work |  | Maint
|  |  |  | U | SRI | U | SRI
1
2
3
4
5
6
7
8
9
10

## Ag_R12
Agenda-R12
Review of Staff postion at PIU
S.No. | CGM | District | PIU | Sanctioned Staff |  |  | Staff in Place |  |  | Remarks
|  |  |  | AM | AO | SE | AM | AO | SE

## Discussion
Points for discussion on PMGSY-III
- | Strategy
- | SQC